## Sheet1
ID | Trust ID | Submission ID | Meta Submission ID | Research Ethics Committee Reference Number | Name of Trial | Target number of patients available | Target number of patients | Date Agreed to recruit target number of patients available | Date Agreed to recruit target number of patients | Trial Status | Target met within the agreed time | Comments | Added By User ID | Amended By User ID | Date Added | Date Amended | Errors
33766 | 926 | 1075 | 25 | 11/LO/0718 | PEPSE | Available | 60 | Available | 2013-10-03 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33767 | 926 | 1075 | 25 | 11/LO/1500 | Nitrite AMI | Available | 80 | Available | 2013-04-01 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33768 | 926 | 1075 | 25 | 10/MRE09/27 | AML 18 Pilot Trial | Available | 8 | Available | 2013-06-30 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33769 | 926 | 1075 | 25 | 11/LO/1621 | 4C | Available | 1100 | Available | 2013-12-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33770 | 926 | 1075 | 25 | 11/NW/0338 | 1108 COPD study | Available | 6 | Available | 2015-03-01 | Open | N/A | Screening started | Unknown | Unknown | 2013-10-30 | 2014-10-29
33771 | 926 | 1075 | 25 | 10/H0711/71 | A Prospective Randomised Study of Early Robotic Ablation by Substrate Elimination of Ventricular Tachycardia (ERASE-VT) | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33772 | 926 | 1075 | 25 | 12/SC/0121 | NN2211-3916 - Study of liraglutide in patients with type 2 diabetes and moderate renal impairment | Available | 6 | Available | 2013-11-16 | Open | N/A | Due to high number of screen failures, recruitment window extended | Unknown | Unknown | 2013-10-30 | 2014-10-29
33773 | 926 | 1075 | 25 | 09/H0716/54 | Genetics of Subarachnoid Haemorrhage (RP4) | Available | 22 | Available | 2014-01-14 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33774 | 926 | 1075 | 25 | 06/Q0508/64 | CoolNEC | Available | 20 | Available | 2013-09-26 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33775 | 926 | 1075 | 25 | 11/LO/1941 | Study of Icatibant in Idiopathic Angioedema | Available | 10 | Available | 2014-12-31 | In set up | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33776 | 926 | 1075 | 25 | 11/LO/0036 | The role of gastro-oesophageal reflux and oesophageal motility disorders in children with feeding difficulties and faltering growth. | Available | 40 | Available | 2014-01-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33777 | 926 | 1075 | 25 | 12/LO/0268 | VX-95-HPC3008 | Available | 4 | Available | 2013-07-04 | Open | N | Ongoing recruitment | Unknown | Unknown | 2013-10-30 | 2014-10-29
33778 | 926 | 1075 | 25 | 09/H1306/54 | ARCTIC | Available | 4 | Available | 2013-05-16 | Closed - In Follow Up | N | The Arctic study recruited 1 patient, an interim analysis was done in October 2012 showing standard treatment was better and the study closed early. | Unknown | Unknown | 2013-10-30 | 2014-10-29
33779 | 926 | 1075 | 25 | 12/LO/0008 | GAMMA | Available | 43 | Available | 2018-11-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33780 | 926 | 1075 | 25 | 12/LO/0057 | GMK Sphere Total knee replacement Surveillance study | Available | 100 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33781 | 926 | 1075 | 25 | 12/LO/0835 | ?Effect of prokinetic therapy on severe oesophageal hypomotility in patients with dysphagia or gastroesophageal reflux.? | Available | 49 | Available | 2014-03-01 | Open | N/A | This is a pilot study and definite number of the participants will depend on the standard deviation of the results | Unknown | Unknown | 2013-10-30 | 2014-10-29
33782 | 926 | 1075 | 25 | 12/LO/0049 | The association between congenital talipes equinovrus (CTEV) and developmental dysplasia of the hip (DDH) | Available | 100 | Available | 2012-11-01 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33783 | 926 | 1075 | 25 | 10/H0707/93 | Lapatinib brain penetration PET study | Available | 3 | Available | 2013-07-19 | Open | N | The study is now open to recruitment . No patients have been recruited to date | Unknown | Unknown | 2013-10-30 | 2014-10-29
33784 | 926 | 1075 | 25 | 10/H0722/42 | PROMISE. Protocolised Management In Sepsis: A multi-centre, randomised controlled trial of the clinical and cost-effectiveness of early, goal-directed, protocolised resuscitation for emerging septic shock. | Available | 14 | Available | 2013-12-31 | Open | N/A | We have increased staffing levels to increase recruitment to this target and this should come in to affect from March 2013 | Unknown | Unknown | 2013-10-30 | 2014-10-29
33785 | 926 | 1075 | 25 | 08/S0703/123 | SUCCINCT | Available | 3 | Available | 2013-09-01 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33786 | 926 | 1075 | 25 | 12/EE/0165 | Extension Phase to Evaluate the Efficacy and Safety of Oral E5501 versus Eltrombopag, in Adults with Chronic Immune Thrombocytopenia (Idiopathic Th | Available | 5 | Available | 2012-09-06 | Withdrawn | N | Study delayed as waiting for IMP to be shipped to ste | Unknown | Unknown | 2013-10-30 | 2014-10-29
33787 | 926 | 1075 | 25 | 12/SC/0185 | DEB2312 | Available | 13 | Available | 2013-09-19 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33788 | 926 | 1075 | 25 | 12/LO/0524 | ADI-PEG small cell | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33789 | 926 | 1075 | 25 | 12/LO/1312 | RFN for SIJ Disease Study | Available | 30 | Available | 2013-09-26 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33790 | 926 | 1075 | 25 | 12/LO/0482 | PERUSE | Available | 5 | Available | 2013-09-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33791 | 926 | 1075 | 25 | 12/EM/0286 | MEPO MEA115588 | Available | 1 | Available | 2013-11-07 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33792 | 926 | 1075 | 25 | 11/NW/0782 | POUT | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33793 | 926 | 1075 | 25 | 12/LO/0720 | MEDI-551 | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33794 | 926 | 1075 | 25 | 12/LO/1313 | ROX CONTROL HTN STUDY: Protocol RH02 Version 1.0, June 20, 2012 | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33795 | 926 | 1075 | 25 | 12/LO/0869 | The Acute Effects Of COPD Treatment On Cardiovascular Function HZC116601 | Available | 49 | Available | 2013-11-02 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33796 | 926 | 1075 | 25 | 12/LO/0858 | M13-101 | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33797 | 926 | 1075 | 25 | 11/LO/0958 | Fast Forward | Available | 20 | Available | 2016-03-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33798 | 926 | 1075 | 25 | 11/SW/0036 | TABLET | Available | 90 | Available | 2014-03-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33799 | 926 | 1075 | 25 | 12/LO/0361 | #0802: The GRANVIA?-C | Available | 15 | Available | 2013-12-31 | In set up | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33800 | 926 | 1075 | 25 | 12/EM/0284 | MEPO 115666 | Available | 4 | Available | 2031-04-21 | Open | Y | Target date checked | Unknown | Unknown | 2013-10-30 | 2014-10-29
33801 | 926 | 1075 | 25 | 12/SC/0098 | SAS115359 Asthma | Available | 30 | Available | 2016-03-01 | In set up | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33802 | 926 | 1075 | 25 | 11/LO/1904 | QBX | Available | 8 | Available | 2014-08-01 | Withdrawn | N/A | Closed Before initiation | Unknown | Unknown | 2013-10-30 | 2014-10-29
33803 | 926 | 1075 | 25 | 06/Q2604/109 | The Stroke Oxygen Study | Available | 12 | Available | 2014-04-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33804 | 926 | 1075 | 25 | 12/NW/0180 | Dialysis Solution Study | Available | 10 | Available | 2014-11-30 | Open | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33805 | 926 | 1075 | 25 | 12/WM/0087 | RAVVA | Available | 6 | Available | 2014-04-15 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33806 | 926 | 1075 | 25 | 12/YH/0342 | PROVHILO | Available | 96 | Available | 2013-11-22 | Closed - In Follow Up | N/A | Recruitment closed early than expected as total study target met | Unknown | Unknown | 2013-10-30 | 2014-10-29
33807 | 926 | 1075 | 25 | 12/LO/1506 | HGS Lupus OSA82017 | Available | 4 | Available | 2015-02-28 | Open | N/A | Patients have been screened but failed to reach target. The 70d benchmark is not really relevant as the incidence of patients presenting to the department with the inclusion and exclusion criteria is very low (hence we only expect to recruit 4 patients over 2 years) | Unknown | Unknown | 2013-10-30 | 2014-10-29
33808 | 926 | 1075 | 25 | 12/LO/0515 | OPTIMA | Available | 5 | Available | 2014-04-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33809 | 926 | 1075 | 25 | 12/LO/0979 | SPARK Btk inhibitor PCI-32765, phase 2 study in relapsed or refractory MCLPCI32765MCL2001 | Available | 5 | Available | 2013-08-30 | In set up | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33810 | 926 | 1075 | 25 | 12/YH/0248 | N01395 Epilepsy | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33811 | 926 | 1075 | 25 | 09/H0805/58 | POM-0 | Available | 20 | Available | 2013-11-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33812 | 926 | 1075 | 25 | 12/LO/0593 | Daratumumab with lenalidomide and dexamethasone in multiple myeloma (GEN503) | Available | 10 | Available | 2015-06-01 | Suspended | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33813 | 926 | 1075 | 25 | 12/LO/0481 | Teveten Study | Available | 8 | Available | 2013-03-31 | Closed - In Follow Up | Y | 21 patients screened. | Unknown | Unknown | 2013-10-30 | 2014-10-29
33814 | 926 | 1075 | 25 | 11/SC/0429 | ISOC-2 | Available | 20 | Available | 2014-08-09 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33815 | 926 | 1075 | 25 | 12/WM0027 | GEKO | Available | 10 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33816 | 926 | 1075 | 25 | 11/LO/1857 | Neomero-2 | Available | 2 | No Date Agreed With Sponsor |  | In set up | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33817 | 926 | 1075 | 25 | 12/YH/0236 | HUBBLE | Available | 30 | Available | 2014-01-22 | Open | N/A | start date considered to be 22/01/2013 and recruitment lasts for 12 months, with 12 month follow-up | Unknown | Unknown | 2013-10-30 | 2014-10-29
33818 | 926 | 1075 | 25 | 12/LO/1553 | Blood pressure in extremely premature newborn infants | Available | 60 | Available | 2015-02-08 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33819 | 926 | 1075 | 25 | 12/LO/1987 | Toxins And Delivery in E-cigarette USers (TADEUS) | Available | 40 | Available | 2013-09-01 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33820 | 926 | 1075 | 25 | 11/WS/0114 | ARISTACAT | Available | 6 | Available | 2014-08-24 | Open | N/A | screened 1 patient but decline | Unknown | Unknown | 2013-10-30 | 2014-10-29
33821 | 926 | 1075 | 25 | 13/SD/0029 | SPORTSMART Pilot Trial | Available | 724 | Available | 2013-08-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33822 | 926 | 1075 | 25 | 12/LO/1590 | BI 1241.36 | Available | 5 | Available | 2013-12-31 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33823 | 926 | 1075 | 25 | 09/H1302/44 | Eurotherm 3235 | Available | 16 | Available | 2017-02-13 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33824 | 926 | 1075 | 25 | 13/SC/0029 | PAE in normal population | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A | No target or date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33825 | 926 | 1075 | 25 | 06/Q0411/82 | Operative vs nonoperative management of midshaft clavicle fractures | Available | 20 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33826 | 926 | 1075 | 25 | 12/LO/1176 | STREAMLINE-C | Available | 90 | Available | 2015-11-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33827 | 926 | 1075 | 25 | 11/LO/0376 | CanTalk | Available | 20 | Available | 2014-08-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33828 | 926 | 1075 | 25 | 12/NW/0513 | SALVO trial to assess cell SALVage in Obstetrics_V1.0_25April2012 | Available | 96 | Available | 2015-03-31 | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33829 | 926 | 1075 | 25 | 12/LO/1177 | STREAMLINE-L | Available | 18 | Available | 2015-12-23 | Open | N/A | Site activated on 24/04/13 | Unknown | Unknown | 2013-10-30 | 2014-10-29
33830 | 926 | 1075 | 25 | 12/NE/0242 | SHINE study | Available | 6000 | Available | 2013-06-30 | Closed - In Follow Up | Y | Number of paitent checked | Unknown | Unknown | 2013-10-30 | 2014-10-29
33831 | 926 | 1075 | 25 | 11/YH/0006 | MERIDIAN | Available | 75 | Available | 2014-07-01 | Withdrawn | N/A | Closed by sponsor before recruitment started | Unknown | Unknown | 2013-10-30 | 2014-10-29
33832 | 926 | 1075 | 25 | MD | EnligHTN II | Available | 40 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33833 | 926 | 1075 | 25 | 12/LO/1223 | Evaluation of PegIFN Lambda/Daclatasvir/Ribavirin in G2 and G3 HCV | Available | 7 | Available | 2013-06-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33834 | 926 | 1075 | 25 | 12/EE/0358 | acid induced hypersensitivity in healthy volunteers | Available | 20 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33835 | 926 | 1075 | 25 | 12/EE/0359 | oesophageal pain hypersensitivity in patients with reflux | Available | 30 | Available | 2013-12-01 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33836 | 926 | 1075 | 25 | 12/LO/1476 | C21013 | Available | 24 | No Date Agreed With Sponsor |  | Withdrawn | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33837 | 926 | 1075 | 25 | 11/LO/1588 | MARCH Study | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33838 | 926 | 1075 | 25 | 12/LO/1598 | TURQUOISE II | Available | 6 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33839 | 926 | 1075 | 25 | 12/EE/0178 | BEACON | Available | 3 | Available | 2014-12-14 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33840 | 926 | 1075 | 25 | 11/SC/0151 | PASTIES | Available | 50 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33841 | 926 | 1075 | 25 | 12/LO/0965 | MUK-6 | Available | 6 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33842 | 926 | 1075 | 25 | 11/LO/1455 | Gilead GS-US-248-122 study | Available | 6 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33843 | 926 | 1075 | 25 | 11/LO/1456 | Gilead GS-US-248-123 study | Available | 6 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33844 | 926 | 1075 | 25 | 12/LO/1168 | R2W | Available | 3 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33845 | 926 | 1075 | 25 | 12/LO/1717 | ZEBRA | Available | 10 | Available | 2014-02-28 | Open | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33846 | 926 | 1075 | 25 | 12/WA/0307 | Resistance to Rituximab versus Tocilizumab in Rheumatoid Arthritis patients (R4-RA) | Available | 80 | Available | 2015-02-13 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33847 | 926 | 1075 | 25 | 10/H0711/99 | ASCOT 10 STUDY | Available | 500 | Available | 2014-08-01 | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33848 | 926 | 1075 | 25 | 12/LO/1130 | Biosimilar (B3281001) | Available | 2 | Available | 2014-01-31 | Closed - In Follow Up | Y | this number is final as recruitment opened on closed on 10/4/2013 | Unknown | Unknown | 2013-10-30 | 2014-10-29
33849 | 926 | 1075 | 25 | 12/WA/0365 | Study to test Apremilast (CC10004) | Available | 4 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33850 | 926 | 1075 | 25 | 10/H1005/6 | DARS | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33851 | 926 | 1075 | 25 | 12/NW/0766 | PREDNOS 2 | Available | 2 | Available | 2014-12-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33852 | 926 | 1075 | 25 | 12/LO/1289 | PROUD | Available | 60 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33853 | 926 | 1075 | 25 | 12/LO/1748 | GS-US-337-0102 | Available | 8 | Available | 2013-06-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33854 | 926 | 1075 | 25 | 12/LO/1986 | M11-646 | Available | 8 | Available | 2013-12-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33855 | 926 | 1075 | 25 | 12/EE/0400 | GS-US-334-0109 Extension study of GS7977 in patients with HCV infection | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33856 | 926 | 1075 | 25 | 13/NW/0026 | Cytokentics ALS study Tirasemtiv | Available | 6 | Available | 2014-07-17 | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33857 | 926 | 1075 | 25 | 12/LO/1861 | JNJ 3002 Ablation in AF | Available | 3 | Available | 2014-06-30 | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33858 | 926 | 1075 | 25 | 12/YH/0401 | MCL 3001 RAY | Available | 2 | No Date Agreed With Sponsor |  | Open | N/A | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33859 | 926 | 1075 | 25 | 12/LO/1890 | AZ Nimbus | Available | 5 | No Date Agreed With Sponsor |  | Closed - Follow Up Complete | N | No target date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33860 | 926 | 1075 | 25 | 13/LO/0006 | GS-US-334-0124 PHOTON 2 | Available | 5 | Available | 2013-06-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33861 | 926 | 1075 | 25 | 12/LO/1628 | SPD476-112 Paediatric PK Ulcerative Colitis Study, version number: 6.0,04SEP2012 | Available | 2 | Available | 2013-06-26 | Withdrawn | N/A | Study was closed by FDA prior to recruitment | Unknown | Unknown | 2013-10-30 | 2014-10-29
33862 | 926 | 1075 | 25 | 12/LO/1635 | PEntoxifylline in Anaemia Resistant to erythropoietin (PEAR) | Available | 100 | Available | 2013-12-31 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33863 | 926 | 1075 | 25 | 11/LO/1559 | OPPORTUNE | Available | 20 | Available | 2014-01-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33864 | 926 | 1075 | 25 | 12/YH/0462 | Medvance Migraine study | Available | 30 | No Date Agreed With Sponsor |  | Open | N | no date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33865 | 926 | 1075 | 25 | 11/LO/1436 | ART study | Available | 3 | Available | 2014-04-25 | Open | N/A | no date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33866 | 926 | 1075 | 25 | 07/Q1604/33 | GROINSS VII | Available | 15 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed as yet | Unknown | Unknown | 2013-10-30 | 2014-10-29
33867 | 926 | 1075 | 25 | 11/LO/1865 | TAK-491 | Available | 4 | Available | 2012-05-03 | Closed - In Follow Up | N | Recruitment was extremely difficult due to complex inclusion/exclusion criteria. Three patients were recruited. | Unknown | Unknown | 2013-10-30 | 2014-10-29
33868 | 926 | 1075 | 25 | 10/NIR02/64 | A Prospective Multicenter Randomized Study Comparing Photoselective Vaporization of the Prostate with the GreenLight XPS? Laser System and Transurethral Resection of the Prostate for the Treatment of Benign Prostatic Hyperplasia | Available | 10 | Available | 2013-04-14 | Open | N | Actively recruiting | Unknown | Unknown | 2013-10-30 | 2014-10-29
33869 | 926 | 1075 | 25 | 12/WS/006 | study to evaluate the effect of dalcetrapib 600mg on cardiovascular (CV) events in adult patients with stable coronary heart disease (CHD), CHD risk equivalents or at elevated risk | Available | 20 | Available | 2008-09-23 | Withdrawn | N/A | This study was cancelled the day before the study initiation | Unknown | Unknown | 2013-10-30 | 2014-10-29
33870 | 926 | 1075 | 25 | 11/LO/1950 | OIC D3820 | Available | 0 | No Date Agreed With Sponsor |  | Withdrawn | N/A | [Study] never started and is closed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33871 | 926 | 1075 | 25 | 11/LO/1040 | ROCHE NV22688 | Available | 3 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33872 | 926 | 1075 | 25 | 08/MRE00/6 | OPPTIMUM - Does progesterone prophylaxis to prevent preterm labour improve outcome? - a randomised double blind placebo controlled trial | Available | 77 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33873 | 926 | 1075 | 25 | 11/NW/0765 | Medicines for Neonates; Data Sharing in Neonatal Services | Available | 25 | Available | 2012-09-01 | Closed - In Follow Up | N | 14 subjects completed surveys | Unknown | Unknown | 2013-10-30 | 2014-10-29
33874 | 926 | 1075 | 25 | 12/LO/0068 | Sipuleucel-T Manufacturing Demonstration Study, ver .01 | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33875 | 926 | 1075 | 25 | 11/LO/1740 | A4001095-MODERN | Available | 5 | Available | 2013-05-30 | Closed - In Follow Up | Y | CLOSED TO RECRUITMENT | Unknown | Unknown | 2013-10-30 | 2014-10-29
33876 | 926 | 1075 | 25 | 12/NW/0034 | Efficacy and safety of CD5024 1% cream versus metronidazole 0.75% cream in subjects with papulopustular rosacea over 16 weeks treatment, followed by a 36-week extension period. | Available | 16 | Available | 2012-05-09 | Closed - In Follow Up | N | Recruited 8 to date due to close to recruitment on 31/10 | Unknown | Unknown | 2013-10-30 | 2014-10-29
33877 | 926 | 1075 | 25 | 11/WM/0164 | EMPIRE - AntiEpileptic drug Monitoring in PREgnancy: An evaluation of effectiveness, cost-effectiveness and acceptability of dose monitoring strategies | Available | 20 | Available | 2015-06-11 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33878 | 926 | 1075 | 25 | 11/EM/0281 | MEDAL: MRI to Establish Diagnosis Against LaparoscopyCan magnetic resonance imaging (MRI) scan replace or triage the use of laparoscopy in establishing a diagnosis among women presenting in secondary care with chronic pelvic pain (CPP)? | Available | 200 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33879 | 926 | 1075 | 25 | 12/LO/0098 | AIN457 (seculinumab) | Available | 3 | No Date Agreed With Sponsor |  | Withdrawn | N/A | Total target was met at other sites 9.11.11 | Unknown | Unknown | 2013-10-30 | 2014-10-29
33880 | 926 | 1075 | 25 | 11/YH/0140 | LUMINOUS. Study to observe the effectiveness and safety of LUCENTIS? through individualized patient treatment and associated outcomes | Available | 70 | Available | 2012-05-30 | Open | N | Still actively recruiting | Unknown | Unknown | 2013-10-30 | 2014-10-29
33881 | 926 | 1075 | 25 | 12/LO/0456 | PCD4989g | Available | 8 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33882 | 926 | 1075 | 25 | 12/SC/0117 | Refining animal emesis studies by defining human nausea biomarkers | Available | 30 | Available | 2012-12-09 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33883 | 926 | 1075 | 25 | 11/NE/0279 | Inflamatory markers, drug and antibody levels in Crohn's disease | Available | 30 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33884 | 926 | 1075 | 25 | 12/NE/0114 | Fast-L | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33885 | 926 | 1075 | 25 | 12/LO/0928 | MASERATI 100: A prospective, multi-center, post-market, single-arm observational study to collect clinical outcome data on the use of PermacolTM Collagen Paste in the treatment on anorectal fistulas | Available | 20 | Available | 2012-08-09 | Closed - In Follow Up | Y | Actively recruiting | Unknown | Unknown | 2013-10-30 | 2014-10-29
33886 | 926 | 1075 | 25 | 11/LO/1812 | STUDY OF THE EFFICACY AND SAFETY OF 2 ORAL DOSES OF CP-690,550 AND 1 SUBCUTANEOUS DOSE OF ETANERCEPT IN SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIAS | Available | 6 | Available | 2012-08-23 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33887 | 926 | 1075 | 25 | 11/L0/0985 | ProMISe - Protocolised Management in Sepsis: A multicentre, randomised controlled trial of the clinical and costeffectivenessof early goaldirectedprotocolised resuscitation for emerging septic shock | Available | 14 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33888 | 926 | 1075 | 25 | 08/NIR03/82 | RT3VIN: A randomised phase II multi-centre clnical trial of topical treatment in women with vulval intraepithelial neoplasia. | Available | 5 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | no target or date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33889 | 926 | 1075 | 25 | 12/EE/0176 | evaluate the efficacy and safety of tapering methotrexate (MTX) dosage versus maintaining the dosage in patients with severe active Rheumatoid Arthritis (RA) who have demonstrated an | Available | 8 | Available | 2012-09-11 | Open | N | Actively recruiting | Unknown | Unknown | 2013-10-30 | 2014-10-29
33890 | 926 | 1075 | 25 | 12/EM/0308 | study of subcutaneous secukinumab in prefilled syringes, assessing long-term safety, tolerability and efficacy in subjects with moderate to severe chronic plaque-type psoriasis | Available | 5 | Available | 2012-09-28 | Closed - In Follow Up | N | Extension study recruitment open only to those who have been on phase 1 | Unknown | Unknown | 2013-10-30 | 2014-10-29
33891 | 926 | 1075 | 25 | 12/EE/0274 | CRASH 3 | Available | 50 | Available | 2017-01-01 | Open | N/A | On target to achieve recruitment targets | Unknown | Unknown | 2013-10-30 | 2014-10-29
33892 | 926 | 1075 | 25 | NA | Association between Shisha Exposure and alveolar Macrophage Carbon. V1 | Available | 50 | Available | 2013-04-18 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33893 | 926 | 1075 | 25 | 11/NW/0246 | STAR | Available | 6 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33894 | 926 | 1075 | 25 | 12/NE/0266 | GS-US-334-0133 | Available | 5 | Available | 2012-12-31 | Closed - In Follow Up | Y | STUDY CLOSED TO RECRUITMENT, TARGET MET. | Unknown | Unknown | 2013-10-30 | 2014-10-29
33895 | 926 | 1075 | 25 | 12/LO/0590 | VX-222 in Subjects With Genotype1 Chronic HepC & Compensated Cirrhosis. VX11-222-106 | Available | 4 | No Date Agreed With Sponsor |  | Withdrawn | N/A | STUDY CLOSED TO RECRUITMENT WITHIN 10DAYS OF APPROVAL. | Unknown | Unknown | 2013-10-30 | 2014-10-29
33896 | 926 | 1075 | 25 | 11/LO/0985 | Randomised clinical trial testing a 1-week course of curative whole breast radiotherapy against a standard 3-week schedule in terms of local cancer control and late adverse effects in patients with early breast cancer. (FAST FORWARD). | Available | 14 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33897 | 926 | 1075 | 25 | 10/H1008/122 | PREDnisolone in NephrOtic Syndrome: The PREDNOS studyLong-term tapering versus standard prednisolone (steroid) therapy for the treatment of the initial episode of childhood nephrotic syndrome: national multicentre randomised double blind trial | Available | 2 | Available | 2014-06-10 | Open | N/A | This is a very rare disease and centre has not seen a new case or eligible NS case since approval to commence study | Unknown | Unknown | 2013-10-30 | 2014-10-29
33898 | 926 | 1075 | 25 | 11/L1/0985 | ProMISe - Protocolised Management in Sepsis: A multicentre, randomised controlled trial of the clinical and costeffectivenessof early goaldirectedprotocolised resuscitation for emerging septic shock | Available | 14 | No Date Agreed With Sponsor |  | Open | N/A | No date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33899 | 926 | 1075 | 25 | 12/NE/0034 | ATTRACT ROSACEA : Efficacy and safety of CD5024 1% cream versus metronidazole 0.75% cream in subjects with papulopustular rosacea over 16 weeks treatment, followed by a 36-week extension period. | Available | 16 | Available | 2012-12-30 | Closed - In Follow Up | N | 15 recruited | Unknown | Unknown | 2013-10-30 | 2014-10-29
33900 | 926 | 1075 | 25 | 09/S802/56 | PROSPECT: PROlapse Surgery: Pragmatic Evaluation and randomised Controlled Trials. | Available | 40 | No Date Agreed With Sponsor |  | Open | N/A | no date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33901 | 926 | 1075 | 25 | 11/YN/0140 | LUMINOUS. Study to observe the effectiveness and safety of LUCENTIS? through individualized patient treatment and associated outcomes | Available | 60 | Available | 2015-03-01 | Open | N/A | lack of eligible patients | Unknown | Unknown | 2013-10-30 | 2014-10-29
33902 | 926 | 1075 | 25 | 12/WM/0117 | evaluate the efficacy and safety of Certolizumab Pegol in combination with methotrexate for inducing and sustaining clinical response in the treatment of DMARD-na?ve adults with | Available | 5 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | no date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33903 | 926 | 1075 | 25 | 11/WM/0220 | TEAMM. Tackling Early Morbidity and Mortality in Myeloma: Assessing the benefit of antibiotic prophylaxis and its effect on healthcare assosciated infections. | Available | 5 | Available | 2014-01-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33904 | 926 | 1075 | 25 | 11/WM/0248 | PREP. Development and validation of a prediction model for risk of complications in early onset pre-eclampsia. | Available | 36 | Available | 2014-04-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33905 | 926 | 1075 | 25 | 11/EM/021 | MEDAL: Can magnetic resonance imaging (MRI) scan replace or triage the use of laparoscopy in establishing a diagnosis among women presenting in secondary | Available | 20 | Available | 2013-09-30 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33906 | 926 | 1075 | 25 | 12/NE/0198 | efficacy of certolizumab pegol plus methotraxate compared with adalimumab plus methotrexate in subjects with moderate to severe rheumatoid arthritis re | Available | 6 | Available | 2013-10-01 | Open | N/A | Nationally recruitment is slow | Unknown | Unknown | 2013-10-30 | 2014-10-29
33907 | 926 | 1075 | 25 | 12/YH/0262 | ALIGN: Multi-country, cross sectionAL study to determine patient specIfic and General beliefs towards medicatioN and their treatment compliance to selected | Available | 18 | No Date Agreed With Sponsor |  | Open | N/A | no date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33908 | 926 | 1075 | 25 | 12/EM/0309 | CAIN 4575 F2310: A randomized, double-blind, placebo-controlled phase III multicenter study of subcutaneous secukinumab in prefilled syringes to demonstrate | Available | 12 | Available | 2013-05-01 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33909 | 926 | 1075 | 25 | 12/WM/0193 | Furiex 3001: A Randomized, Double-blind, Placebo-controlled, Phase 3 Study to Evaluate the Efficacy, Safety, and Tolerability of JNJ-27018966 in the Treatment | Available | 4 | Available | 2013-05-01 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33910 | 926 | 1075 | 25 | 10/H0709/91 | Novel Biomarkers to Predict Outcome in Clostridium Difficile Infection (CDI)? | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A | no target or date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33911 | 926 | 1075 | 25 | 12/YN/0236 | HUBBLE: A multi-centre randomised controlled trial comparing rubber band ligation with haemorrhoidal artery ligation in the management of symptomatic second and third degree haemorrhoids. | Available | 30 | Available | 2014-01-16 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33912 | 926 | 1075 | 25 | 12/ES/0074 | study of subcutaneous secukinumab in prefilled syringes to demonstrate long-term efficacy, safety and tolerability up to 2 years in subjects with moderate to severe chronic plaqu | Available | 4 | No Date Agreed With Sponsor |  | Closed - In Follow Up | Y | no date agreed | Unknown | Unknown | 2013-10-30 | 2014-10-29
33913 | 926 | 1075 | 25 | 12/LO/1129 | pharmacokinetics and pharmacodynamics, and assessing the safety of PF-05280586 and rituximab in subjects with active rheumatoid arthritis on a background of methotrexate who have had an inadequate r | Available | 3 | Available | 2013-06-01 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33914 | 926 | 1075 | 25 | 12/SC/0570 | PASSAGE | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33915 | 926 | 1075 | 25 | 11/WM/0288 | Desktop III | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33916 | 926 | 1075 | 25 | 13/SC/0087 | Anal sensorimotor effects of neuromodulation | Available | 120 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33917 | 926 | 1075 | 25 | 13/LO/0472 | Ultrasound Vasculature | Available | 33 | Available | 2014-04-30 | Closed - Follow Up Complete | Y |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33918 | 926 | 1075 | 25 | 13/LO/0094 | HAPPY London | Available | 400 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33919 | 926 | 1075 | 25 | 13/LO/0077 | The HALT Hepatitis Study | Available | 8 | Available | 2015-03-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33920 | 926 | 1075 | 25 | 12/LO/1378 | PBS Study | Available | 15 | Available | 2015-06-30 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33921 | 926 | 1075 | 25 | 11/LO/1333 | MiPEP | Available | 40 | Available | 2014-02-28 | Open | N |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33922 | 926 | 1075 | 25 | 13/EM/0095 | CAIN457F2312 | Available | 5 | Available | 2013-10-01 | Closed - In Follow Up | Y |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33923 | 926 | 1075 | 25 | 12/EE/0371 | Phase III Study Comparing Betrixiban with Enoxaparin in VTE | Available | 8 | Available | 2014-03-30 | Open | N |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33924 | 926 | 1075 | 25 | 12/NE/0367 | GSK SHIELD | Available | 2 | Available | 2014-08-31 | Withdrawn | N/A | The study has been closed by the sponsor. No patients recruited as it was closed within a few weeks of being initiated | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33925 | 926 | 1075 | 25 | 12/EE/0544 | INSPIRE | Available | 24 | Available | 2013-12-31 | Open | N |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33926 | 926 | 1075 | 25 | 12/LO/1653 | NEPTUNE | Available | 136 | Available | 2017-12-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33927 | 926 | 1075 | 25 | 13/SC/0092 | Siponimod BAF312 | Available | 6 | Available | 2014-03-30 | Open | N |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33928 | 926 | 1075 | 25 | 12/WA/0308 | Lilly RHAP PsA study | Available | 4 | Available | 2014-10-31 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33929 | 926 | 1075 | 25 | 10/MRE09/10 | StAmP | Available | 10 | Available | 2014-05-31 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33930 | 926 | 1075 | 25 | 11/SC/0282 | RADVAN | Available | 6 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33931 | 926 | 1075 | 25 | 11/WM/0287 | Lilly JADZ RA Study | Available | 5 | Available | 2015-02-09 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33932 | 926 | 1075 | 25 | 13/SC/0021 | 14V-MC-JADV | Available | 4 | Available | 2014-04-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33933 | 926 | 1075 | 25 | 12/EE/0349 | BriTROC-1 | Available | 12 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33934 | 926 | 1075 | 25 | 11/SC/0417 | Serum creatinine changes after critical illness and implications for diagnosis of chronic kidney | Available | 750 | Available | 2013-07-31 | Closed - In Follow Up | Y |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33935 | 926 | 1075 | 25 | 11/LO/2026 | EBNA1 IgG predicts SPMS | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33936 | 926 | 1075 | 25 | 11/LO/1540 | GWAS | Available | 50 | Available | 2015-07-24 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33937 | 926 | 1075 | 25 | 13/L0/0257 | Genetic Factors Affecting the Timing of Puberty | Available | 200 | Available | 2015-09-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33938 | 926 | 1075 | 25 | 11/LO/1543 | Signalling networks in IBD - version 1.0 | Available | 200 | Available | 2016-08-08 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33939 | 926 | 1075 | 25 | 13/LO/0257 | Multiple Myeloma Patient Pathway | Available | 200 | Available | 2015-09-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33940 | 926 | 1075 | 25 | 13/EM/0244 | Technical Evaluation of the Xpert(r) HPV Assay in General Screening Population | Available | 1500 | Available | 2013-10-03 | Closed - In Follow Up | Y |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33941 | 926 | 1075 | 25 | 13/LO/0363 | Patterns of cytokine gene expression in bacteraemic patients (V1) | No Target Agreed With Sponsor |  | Available | 2015-06-21 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33942 | 926 | 1075 | 25 | 13/LO/0130 | Lilly JADW A Randomized, Double-Blind, Placebo-Controlled, Phase 3 Study Evaluating the Efficacy and Safety of Baricitini | Available | 4 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33943 | 926 | 1075 | 25 | 12/LO/1973 | Lilly JADZ RA Study | Available | 6 | Available | 2015-04-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33944 | 926 | 1075 | 25 | 13/SC/0073 | COSMIC-HF A dose escalation study in patients with heart failure | Available | 8 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33945 | 926 | 1075 | 25 | 13/SS/0072 | PROOF study: Patient reported outcomes of Brimonidine Tartrate 0.5% gel for treatment of severe facial erythema of rosacea | Available | 6 | Available | 2013-12-01 | Open | N |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33946 | 926 | 1075 | 25 | 13/LO/0097 | GS-US-321-0105 | Available | 5 | Available | 2014-06-30 | Open | N |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33947 | 926 | 1075 | 25 | 12/WA/0250 | Efficacy, pharmacokinetics, and safety of BI 695500 versus rituximab in patients with moderately to severely active rheumatoid arthritis: a randomized, doubleblind, parallel arm, multiple dose, active comparator trial. | Available | 2 | Available | 2014-09-01 | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33948 | 926 | 1075 | 25 | 13/LO/0033 | PEGGY - A PHASE II, RANDOMIZED STUDY OF PACLITAXEL WITH GDC-0941 VERSUS PACLITAXEL WITH PLACEBO IN PATIENTS WITH LOCALLY RECURRENT OR METASTATIC BREAST CANCER | Available | 2 | No Date Agreed With Sponsor |  | Open | N/A |  | CTP Submission Platform | Unknown | 2013-10-30 | 2014-10-29
33949 | 926 | 1075 | 25 | 12/YH/0318 | GS-US-312-0115 | Available | 2 | Available | 2014-03-31 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33950 | 926 | 1075 | 25 | 13/EE/0038 | HALT IT | Available | 50 | Available | 2014-07-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33951 | 926 | 1075 | 25 | 12/SC/0014 | VANISH | Available | 30 | Available | 2015-05-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33952 | 926 | 1075 | 25 | 13/LO/0135 | METS | Available | 200 | Available | 2016-04-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33953 | 926 | 1075 | 25 | 13/LO/0501 | Maribavir v Valganciclovir in CMV | Available | 10 | Available | 2014-12-03 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33954 | 926 | 1075 | 25 | 13/LO/0530 | Characterising Metastatic Penile Cancer Using Molecular Imaging - Hybrid MRI PET (MRI-PET) | No Target Agreed With Sponsor |  | Available | 2016-03-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33955 | 926 | 1075 | 25 | 13/ES/0013 | UK use of aqueous zanamivir during the 2009 A-H1N1 influenza pandemic | Available | 14 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33956 | 926 | 1075 | 25 | 12/WS/0145 | ATTAIN | Available | 1 | Available | 2015-12-31 | Open | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33957 | 926 | 1075 | 25 | GTAC185 | BNIT PRV 301 | Available | 10 | Available | 2017-03-01 | In set up | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33958 | 926 | 1075 | 25 | 12/WS/0300 | ODYSSEY | Available | 25 | Available | 2014-12-31 | Open | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33959 | 926 | 1075 | 25 | 13/LO/0098 | GS-US-321-0105 | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33960 | 926 | 1075 | 25 | 12/SC/0068 | Does image-localisation of breast tumours affect the rate of reoperation following breast-conserving | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33961 | 926 | 1075 | 25 | 12/LO/1923 | Cough in TB | Available | 60 | Available | 2014-08-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33962 | 926 | 1075 | 25 | 11/EM/0442 | ENCEPH UK/ UK CHIMES | No Target Agreed With Sponsor |  | Available | 2016-08-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33963 | 926 | 1075 | 25 | 12/NW/0361 | SANAD-II | Available | 14 | Available | 2019-01-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33964 | 926 | 1075 | 25 | 09/H0718/45 | SASS Study | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33965 | 926 | 1075 | 25 | 13/LO/0975 | International Ovarian Tumour Analysis (IOTA) Phase 5 | Available | 500 | Available | 2018-08-14 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33966 | 926 | 1075 | 25 | 13/LO/0528 | PIONEER | Available | 8 | Available | 2014-08-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33967 | 926 | 1075 | 25 | 13/LO/0560 | Symbicort Turbohaler | Available | 5 | Available | 2014-05-30 | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33968 | 926 | 1075 | 25 | 13/LO/0315 | BAMI | Available | 180 | Available | 2016-10-01 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33969 | 926 | 1075 | 25 | 13/LO/0322 | Predicting lung function decline in adolescents with CF | Available | 15 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33970 | 926 | 1075 | 25 | 13/LO/0284 | Enhancing the detection of MRD in patients with B-cell malignancies | Available | 100 | Available | 2015-07-31 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33971 | 926 | 1075 | 25 | 09/H0707/88 | NEON | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33972 | 926 | 1075 | 25 | 13/EE/0144 | CAM-3001-1107 | Available | 2 | Available | 2013-04-01 | Open | Y |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33973 | 926 | 1075 | 25 | 13/LO/0891 | Probiotic and assesement of gut function 12.05 NRC | Available | 120 | Available | 2015-06-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33974 | 926 | 1075 | 25 | 13/LO/0215 | Screening for Viral Hepatitis in migrants in East London | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33975 | 926 | 1075 | 25 | PNM/12/13-26 | Multidisciplinary clinical decision making in colorectal cancer teams | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33976 | 926 | 1075 | 25 | 12/LO/0918 | Early Assessment of Circulating Volume in Trauma | Available | 20 | Available | 2014-07-30 | Open | N/A |  | Unknown | Unknown | 2013-10-30 | 2014-10-29
33977 | 926 | 1075 | 25 | 13/LO/0807 | JNJ-38518168 | Available | 4 | Available | 2014-09-01 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33978 | 926 | 1075 | 25 | 13/LO/0855 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Efficacy and Safety of Idelalisib (GS-1101) in Combination with Rituximab for Previously Treated Indolent Non-Hodgkin Lymphomas | Available | 2 | Available | 2020-04-30 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33979 | 926 | 1075 | 25 | 12/NE/0228 | TiLTs-CC | Available | 10 | Available | 2015-10-22 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33980 | 926 | 1075 | 25 | 13/WM/0365 | CAIN457F2306E1 | Available | 4 | Available | 2018-10-01 | Open | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33981 | 926 | 1075 | 25 | 13/SC/0279 | GS-US-292-0109 | Available | 8 | Available | 2014-10-29 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33982 | 926 | 1075 | 25 | 13/EM/0230 | A Phase II Randomized, DoubleBlind, PlaceboControlled, Multicenter Study of VS 6063 in Subjects with Malignant Pleural Mesothelioma | Available | 1 | Available | 2014-12-31 | Open | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33983 | 926 | 1075 | 25 | 13/EE/0276 | GS-US-334-0153 | Available | 25 | Available | 2014-12-12 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33984 | 926 | 1075 | 25 | 005-02-13 | STEP hep | Available | 80 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33985 | 926 | 1075 | 25 | 12/YH/0446 | JNJ 207047 | Available | 3 | Available | 2014-09-01 | Open | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33986 | 926 | 1075 | 25 | 13/YH/0118 | CQVA149A2318 | Available | 5 | Available | 2014-04-01 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33987 | 926 | 1075 | 25 | 13/LO/0784 | FDS-NBU-1034 - Elderly Volunteers Study | Available | 5 | Available | 2014-07-31 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33988 | 926 | 1075 | 25 | 13/LO/0671 | 205MS303 | Available | 8 | Available | 2017-10-01 | Closed - In Follow Up | N |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33989 | 926 | 1075 | 25 | 13/SC/0259 | GS-US-313-0125 | Available | 2 | Available | 2014-10-01 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33990 | 926 | 1075 | 25 | 13/EM/0357 | CAIN457F2305 | Available | 4 | Available | 2017-07-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33991 | 926 | 1075 | 25 | 13/LO/1290 | M13-102 | Available | 12 | Available | 2015-12-01 | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33992 | 926 | 1075 | 25 | 13/EM/1302 | A Phase IIIb randomised, openlabel study of the safety and efficacy of dolutegravir/abacavir/lamivudine once daily compared to atazanavir and ritonavir plus tenofovir/emtricitabine once daily in HIV1 infected antiretroviral therapy naive women. | Available | 3 | Available | 2014-08-31 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33993 | 926 | 1075 | 25 | 11/H1307/6 | SWITCH | Available | 10 | Available | 2015-06-30 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33994 | 926 | 1075 | 25 | 13/WA/0185 | ASSURE | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33995 | 926 | 1075 | 25 | 12/EM/0003 | Induction of labour versus expectant management for nulliparous women over 35 years of age (35/39) | Available | 25 | Available | 2014-07-02 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33996 | 926 | 1075 | 25 | 13/NW/0591 | EPIDEPSO | Available | 10 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33997 | 926 | 1075 | 25 | 13/EE/0201 | COT1-13-01 Illiotibial Band in OA | Available | 6 | Available | 2015-02-28 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33998 | 926 | 1075 | 25 | 13/SC/0463 | CDEB025A2222 | Available | 8 | Available | 2014-12-30 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
33999 | 926 | 1075 | 25 | 13/WS/0211 | TMC435HPC3014 | Available | 5 | Available | 2013-11-29 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34000 | 926 | 1075 | 25 | 13/NW/0464 | A Placebo-Controlled, Multicenter, Double-Blind, Randomized, Pharmacokinetic and Pharmacodynamic Trial of IDN-6556 in Subjects with Acute-on-Chronic Liver Failure | Available | 4 | Available | 2014-03-31 | Open | N |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34001 | 926 | 1075 | 25 | 13/EE/0241 | SIGNATURE | Available | 3 | Available | 2016-03-31 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34002 | 926 | 1075 | 25 | 13/LO/1019 | 215MS201 | Available | 4 | Available | 2014-06-06 | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34003 | 926 | 1075 | 25 | 13/LO/0936 | SUKCES | Available | 350 | Available | 2015-05-04 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34004 | 926 | 1075 | 25 | 13/NW/0598 | RADICAL | Available | 100 | Available | 2014-11-19 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34005 | 926 | 1075 | 25 | 12/YH/0475 | GP28331 - A PHASE Ib study - CHRONIC LYMPHOCYTIC LEUKAEMIA | Available | 4 | Available | 2015-04-15 | In set up | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34006 | 926 | 1075 | 25 | 13/LO/1512 | RCT comparing twin block wear for varying durations | Available | 84 | Available | 2015-03-06 | Open | N |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34007 | 926 | 1075 | 25 | 13/EM/0340 | A Phase 2 OpenLabel Study of the Efficacy of ABT199 (GDC0199) in Subjects with Relapsed or Refractory Chronic Lymphocytic Leukemia Harboring the 17p Deletion | Available | 3 | Available | 2016-10-31 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34008 | 926 | 1075 | 25 | 13/NW/0692 | CARMELINA | Available | 10 | Available | 2016-07-09 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34009 | 926 | 1075 | 25 | 13/LO/1022 | 308: Phase 3 study of XL184 vs Everolimus in subjects with RCC | Available | 10 | Available | 2015-07-31 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34010 | 926 | 1075 | 25 | 13/EM/0353 | Working after Brain Injury Final Version 1.0 | Available | 34 | Available | 2014-08-31 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34011 | 926 | 1075 | 25 | 13/NE/0125 | PRESTO | Available | 5 | Available | 2016-09-01 | Open | N/A |  | Unknown | Unknown | 2014-01-28 | 2014-10-29
34012 | 926 | 1075 | 25 | 12/LO/1950 | C25003 in NHL | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34013 | 926 | 1075 | 25 | 13/LO/0128 | Liily JADX RA study | Available | 5 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34014 | 926 | 1075 | 25 | 12/EE/0171 | A 2 Year mechanistic study of Belimumab in Idiopathic Membranous Glomerulonephropathy | Available | 2 | Available | 2014-01-31 | Open | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34015 | 926 | 1075 | 25 | 13/LO/0572 | GSUS 292 0104 | Available | 7 | Available | 2015-07-01 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34016 | 926 | 1075 | 25 | 13/LO/0574 | GSUS2920111 | Available | 11 | Available | 2015-07-25 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34017 | 926 | 1075 | 25 | 12/NW/0802 | LAQ-MS-305 (CONCERTO) | Available | 6 | Available | 2018-05-07 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34018 | 926 | 1075 | 25 | 13/LO/0002 | GS-US-312-0119 | Available | 2 | Available | 2014-03-01 | Open | N |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34019 | 926 | 1075 | 25 | 13/LO/0736 | EGALITY GP2015 in Plaque Psoriasis | Available | 6 | Available | 2014-12-19 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34020 | 926 | 1075 | 25 | 12/WM/0341 | AMG145 Fourier in CVD | Available | 56 | Available | 2014-08-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34021 | 926 | 1075 | 25 | 13/LO/0499 | ASCERTAIN | Available | 2 | Available | 2018-08-10 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34022 | 926 | 1075 | 25 | 13/LO/0665 | CAIN457A2312 | Available | 4 | Available | 2015-07-30 | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34023 | 926 | 1075 | 25 | 13/LO/0666 | CAIN457A2313 | Available | 6 | Available | 2014-06-01 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34024 | 926 | 1075 | 25 | 13/LO/0983 | GO28625 FIR | Available | 2 | Available | 2015-07-16 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34025 | 926 | 1075 | 25 | 12/LO/1759 | OuTSMART | Available | 600 | Available | 2015-12-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34026 | 926 | 1075 | 25 | 12/LO/1319 | A Phase 2 study for older adults with Acute Lymphoblastic Leukaemia | Available | 2 | Available | 2015-09-01 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34027 | 926 | 1075 | 25 | 11/H0722/8 | Rapid Identification via Interferon Gamma test for Active Tuberculosis | Available | 70 | Available | 2016-02-13 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34028 | 926 | 1075 | 25 | 13/EM/0349 | MANTA | Available | 3 | Available | 2018-05-08 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34029 | 926 | 1075 | 25 | 13/SC/0558 | CAIN457A3301 | Available | 5 | Available | 2016-03-31 | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34030 | 926 | 1075 | 25 | 13/SC/0486 | NOVAP | Available | 63 | Available | 2014-07-01 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34031 | 926 | 1075 | 25 | 04/MRE07/35 | STAMPEDE | Available | 5 | Available | 2015-03-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34032 | 926 | 1075 | 25 | 13/LO/1199 | JADY Extension | Available | 18 | Available | 2017-02-20 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34033 | 926 | 1075 | 25 | 08/H1102/92 | TARDIS | Available | 12 | Available | 2017-06-30 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34034 | 926 | 1075 | 25 | 13/LO/1115 | PIVOTAL | Available | 50 | Available | 2015-09-30 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34035 | 926 | 1075 | 25 | 13/LO/0669 | MINIMISE STEMI trial version 1 | Available | 40 | Available | 2015-03-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34036 | 926 | 1075 | 25 | 13/LO/0576 | Evaluating an automated diabetic retinopathy screening tool | Available | 100 | Available | 2015-12-03 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34037 | 926 | 1075 | 25 | 10/H0302/51 | TB-REACH | Available | 10 | Available | 2014-12-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34038 | 926 | 1075 | 25 | 12/EM/0095 | TOTAL | Available | 10 | Available | 2015-01-29 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34039 | 926 | 1075 | 25 | 13/SW/0186 | EFFECT Efficacy of Fluticasone/Formoterol in COPD Treatment FLT3509 | Available | 1 | Available | 2014-09-30 | Open | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34040 | 926 | 1075 | 25 | 12/NW/0509 | RELIEF | Available | 10 | Available | 2015-12-30 | Closed - In Follow Up | N |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34041 | 926 | 1075 | 25 | 13/LO/1284 | ROX Registry | Available | 10 | Available | 2015-12-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34042 | 926 | 1075 | 25 | 13/LO/1881 | OPUS 1 | Available | 2 | Available | 2014-03-07 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34043 | 926 | 1075 | 25 | 13/LO/1766 | EMR 100070-001: MSB0010718C in subjects with solid tumours | Available | 3 | Available | 2015-01-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34044 | 926 | 1075 | 25 | 13/LO/1513 | CC-5013-NHL-007 Indolent lymphoma: Augment trial | Available | 6 | Available | 2017-02-28 | In set up | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34045 | 926 | 1075 | 25 | 13/YH/0174 | Adalimumab in Non-Radiographic Axial Spondyloarthritis | Available | 5 | Available | 2017-07-31 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34046 | 926 | 1075 | 25 | 13/NW/0791 | GSK1278863 in CKD | Available | 2 | Available | 2014-06-26 | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34047 | 926 | 1075 | 25 | 13/NI/0148 | WB28182 | Available | 5 | Available | 2017-12-01 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34048 | 926 | 1075 | 25 | 13/LO/1490 | GS-US-320-0110 | Available | 5 | Available | 2017-12-01 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34049 | 926 | 1075 | 25 | 13/NE/0260 | OPTI-MIND 2 Protocol 07-12 | Available | 10 | Available | 2015-04-29 | Closed - In Follow Up | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34050 | 926 | 1075 | 25 | 13/LO/1752 | Atopic Dermatitis CIM003JG | Available | 6 | Available | 2014-02-28 | Open | N/A |  | Unknown | Unknown | 2014-04-30 | 2014-10-29
34051 | 926 | 1075 | 25 | 13/LO/0830 | Daclatasvir in HCV and HIV | Available | 5 | No Date Agreed With Sponsor |  | Open | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34052 | 926 | 1075 | 25 | 11/SC/0458 | PACMEL | Available | 4 | Available | 2015-03-31 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34053 | 926 | 1075 | 25 | 13/LO/0704 | VO72.12 STALLERGENES | Available | 4 | No Date Agreed With Sponsor |  | Open | N/A | qualitative study | Unknown | Unknown | 2014-07-23 | 2014-10-29
34054 | 926 | 1075 | 25 | 13/LO/0419 | B3281004 Pfizer Extension Study | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | Closed - Follow Up Complete | N/A | the study was opened to allow patients for phase 1 to enter the extension phase however after analysis participants were all drug non reponders so no-one can was eligible to be enrolled in this study and the study is closed. | Unknown | Unknown | 2014-07-23 | 2014-10-29
34055 | 926 | 1075 | 25 | 13/LO/1302 | A Phase IIIb randomised, openlabel study of the safety and efficacy of dolutegravir/abacavir/lamivudine once daily compared to atazanavir and ritonavir plus tenofovir/emtricitabine once daily in HIV1 infected antiretroviral therapy naive women. | Available | 3 | Available | 2014-08-31 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34056 | 926 | 1075 | 25 | 11/LO/1487 | UKALL 2011 | Available | 15 | Available | 2028-06-09 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34057 | 926 | 1075 | 25 | 13/SC/0325 | GENA-21 | Available | 2 | Available | 2015-04-29 | Open | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34058 | 926 | 1075 | 25 | 13/EE/0099 | WB28850 in Asthma | Available | 130 | No Date Agreed With Sponsor |  | Closed - Follow Up Complete | N |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34059 | 926 | 1075 | 25 | 13/YH/0140 | Ivabradine in heart failure with preserved ejection fraction | Available | 8 | Available | 2015-06-30 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34060 | 926 | 1075 | 25 | 13/WM/0114 | SHINE MCL3002 | Available | 2 | No Date Agreed With Sponsor |  | Closed - In Follow Up | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34061 | 926 | 1075 | 25 | 13/EE/0257 | MK 5172047 | Available | 3 | Available | 2014-03-28 | Closed - Follow Up Complete | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34062 | 926 | 1075 | 25 | 13/LO/1489 | GS-US-320-0108 | Available | 6 | Available | 2014-08-30 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34063 | 926 | 1075 | 25 | 13/SC/0384 | Tremelimumab in PMM | Available | 10 | Available | 2014-12-31 | Closed - Follow Up Complete | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34064 | 926 | 1075 | 25 | 13/NI/0093 | Givinostat in JAK2V617F | Available | 1 | Available | 2014-12-31 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34065 | 926 | 1075 | 25 | 13/LO/1323 | LA38-0411 Iron Overload | Available | 3 | Available | 2014-12-31 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34066 | 926 | 1075 | 25 | 13/EM/0375 | Triple 6 A Phase III Study of CHF5993 in Patients with Severe COPD | Available | 8 | Available | 2015-04-14 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34067 | 926 | 1075 | 25 | 13/NW/0793 | GSK1278863 in CKD | Available | 2 | Available | 2014-09-30 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34068 | 926 | 1075 | 25 | 13/LO/1906 | SAR153191 in RA LTS11210 | Available | 2 | Available | 2019-01-30 | Open | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34069 | 926 | 1075 | 25 | 13/LO/1795 | CSL830_3001 in HAE | Available | 1 | Available | 2015-06-30 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34070 | 926 | 1075 | 25 | 13/LO/1111 | eSTI2 chlamydia clinical care pathway pilot study | Available | 175 | Available | 2016-01-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34071 | 926 | 1075 | 25 | 14/SC/0032 | B1481022 | Available | 20 | Available | 2017-08-28 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34072 | 926 | 1075 | 25 | 14/NW/0006 | Calcipotriol in Psoriasis LP0076-1017 | Available | 3 | Available | 2015-10-30 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34073 | 926 | 1075 | 25 | 14/SC/0033 | B1481038 | Available | 20 | Available | 2014-08-28 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34074 | 926 | 1075 | 25 | 13/EE/0433 | LEADLESS Observational Study | Available | 10 | Available | 2014-10-03 | Closed - In Follow Up | N |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34075 | 926 | 1075 | 25 | 14/EM/0024 | CAIN457F2318 | Available | 4 | Available | 2018-01-22 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34076 | 926 | 1075 | 25 | 14/LO/0083 | CV risk in HIV patients switching from a boosted PI to DTG | Available | 5 | Available | 2016-06-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34077 | 926 | 1075 | 25 | 14/EM/0086 | CAIN2314- 16-week Efficacy and 3-year Safety, Tolerability and Efficacy of Secuk | Available | 5 | Available | 2017-09-18 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34078 | 926 | 1075 | 25 | 11/AL/0319 | Fractures and Bisphosphonates the FaB trial | Available | 20 | Available | 2015-09-30 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34079 | 926 | 1075 | 25 | 14/LO/0451 | Electrical Stimulation use with pelvic fracture rehabilitation Vrs 1 | Available | 12 | Available | 2014-06-30 | Closed - In Follow Up | N |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34080 | 926 | 1075 | 25 | 14/LO/0358 | Electronic cigarettes: Nicotine delivery in users- PK | Available | 7 | Available | 2017-03-03 | Open | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34081 | 926 | 1075 | 25 | 14/SC/0225 | GSUS3111089 Phase 3 double-blind study of F/TAF in HIV-1 positive patients | Available | 10 | Available | 2016-10-31 | Closed - In Follow Up | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34082 | 926 | 1075 | 25 | 13/SC/0495 | RES117287 | Available | 15 | Available | 2015-04-10 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34083 | 926 | 1075 | 25 | 13/SS/0051 | TRIOphysio | Available | 36 | Available | 2017-06-28 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34084 | 926 | 1075 | 25 | 13/SC/0581 | VIOLA (Version 1.0 15Oct2013) | Available | 5 | Available | 2017-01-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34085 | 926 | 1075 | 25 | 13/EE/0151 | CD-IA-CAM-3001-1109 | Available | 2 | Available | 2018-05-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34086 | 926 | 1075 | 25 | 14/LO/0121 | A Phase II, randomized, placebo-controlled study of paclitaxel in combination with the Akt inhibitor AZD5363 in triple-negative advanced or metastatic breast cancer -PAKT | Available | 9 | Available | 2017-01-01 | In set up | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34087 | 926 | 1075 | 25 | 14/WS/0002 | AMVISION1: 20090406 | Available | 5 | Available | 2018-04-17 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34088 | 926 | 1075 | 25 | 13/YH/0162 | HABSelect – Hyaluronic Acid Binding Sperm selection_V1.0 | Available | 900 | Available | 2016-02-28 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34089 | 926 | 1075 | 25 | 14/SC/0104 | D5613C00001 AZD1722 for phosphate lowering in dialysis patients | Available | 4 | Available | 2014-10-03 | Closed - In Follow Up | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34090 | 926 | 1075 | 25 | 13/EM/0195 | EMBRACE Belimumab in SLE | Available | 10 | Available | 2016-05-31 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34091 | 926 | 1075 | 25 | 13/SC/0554 | TRP Novonordisk NN8226-4064 | Available | 2 | Available | 2014-12-31 | Withdrawn | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34092 | 926 | 1075 | 25 | 09/H0709/56 | PEXIVAS | Available | 5 | Available | 2015-07-02 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34093 | 926 | 1075 | 25 | 13/YH/0282 | ACT MOVE ML28641 | Available | 4 | Available | 2017-09-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34094 | 926 | 1075 | 25 | 14/LO/0132 | RAFT-Robotic surgery after focal ablation therapy | Available | 24 | Available | 2017-01-01 | In set up | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34095 | 926 | 1075 | 25 | 14/NW/0008 | MK8259-032 Go Colitis | Available | 12 | Available | 2015-03-31 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34096 | 926 | 1075 | 25 | 13/EM/0423 | GWP42004 in Type 2 diabetes | Available | 8 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34097 | 926 | 1075 | 25 | 13/LO/0881 | NOCTURNAL HYPOGLYCAEMIA | Available | 40 | Available | 2015-01-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34098 | 926 | 1075 | 25 | 14/LO/0022 | WO29074 Randomised Phase II study in untreated advanced renal cell carcinoma | Available | 6 | Available | 2017-11-07 | Open | Y |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34099 | 926 | 1075 | 25 | 14/SC/0100 | A01620 | Available | 6 | Available | 2015-03-30 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34100 | 926 | 1075 | 25 | 12/SS/0138 | RESTART | Available | 6 | Available | 2016-02-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34101 | 926 | 1075 | 25 | 11/SC/0528 | INTERLACE | Available | 25 | Available | 2019-03-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34102 | 926 | 1075 | 25 | 13/YH/0229 | GO2 - Alternative chemotherapy for frailer patients with advanced gastric or oesophageal cancer | Available | 5 | Available | 2016-08-31 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34103 | 926 | 1075 | 25 | 12/LO/1201 | UK Haplo v1.0 | Available | 2 | Available | 2016-11-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34104 | 926 | 1075 | 25 | 12/LO/1822 | PANTHER | Available | 15 | Available | 2016-01-01 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34105 | 926 | 1075 | 25 | 11/WS/0039 | A Phase I/IIa Trial of AZD4547 in combination with CX: The FACING Study | Available | 5 | Available | 2015-03-31 | In set up | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34106 | 926 | 1075 | 25 | 14/SC/0034 | 997HA307 - Previously Treated Subjects With Severe Haemophilia A | Available | 4 | Available | 2016-11-30 | Open | N/A |  | Unknown | Unknown | 2014-07-23 | 2014-10-29
34155 | 926 | 1075 | 25 | 14/EE/1048 | ESTEEM | Available | 1092 | Available | 2015-08-31 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34156 | 926 | 1075 | 25 | 13/EM/0266 | Low dose cyclophosphamide +/- nintedanib in advanced ovarian cancer | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | In set up | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34157 | 926 | 1075 | 25 | 14/LO/0438 | Cook MyoSite AMDC Fecal Incontinence Clinical Study 09025 | Available | 15 | Available | 2015-09-01 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34158 | 926 | 1075 | 25 | 14/NW/0138 | OPTIMIZE RO2455302RD | Available | 5 | Available | 2016-01-29 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34159 | 926 | 1075 | 25 | 13/LO/1517 | DOLOMITES 1517-CL-0610 Phase 3 Study of ASP1517 (FG-4592) | Available | 12 | Available | 2017-09-30 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34160 | 926 | 1075 | 25 | 13/NW/0496 | Pregabalin in subjects with Primary Generalised TonicClonic | Available | 2 | Available | 2014-12-03 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34161 | 926 | 1075 | 25 | 14/NW/0055 | Pregabalin Open Label Follow up study of A0081105 | Available | 2 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34162 | 926 | 1075 | 25 | 13/SS/0132 | COPD: A Phase 2 Randomised, Double-blind, Placebo-controlled, Efficacy and Safety Study of Inhaled JNJ49095397 (RV568) in Subjects with Moderate to Severe Chronic Obstructive Pulmonary Disease. | Available | 7 | Available | 2014-10-31 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34163 | 926 | 1075 | 25 | 14/SC/0178 | GSUS3120123 | No Target Agreed With Sponsor |  | No Date Agreed With Sponsor |  | In set up | N/A | Sit not open yet | Unknown | Unknown | 2014-10-20 | 2014-10-29
34164 | 926 | 1075 | 25 | 11/LO/1570 | CHEMO-T | Available | 10 | Available | 2017-02-13 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34165 | 926 | 1075 | 25 | 13/LO/1473 | TIG3 | Available | 8 | Available | 2015-08-01 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34166 | 926 | 1075 | 25 | 13/NE/0299 | EuroHYP1: European multicentre, randomised, phase III clinical trial of therapeutic hypothermia plus best medical treatment versus best medical treatment alone for acute ischaemic stroke | Available | 6 | Available | 2015-09-01 | In set up | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34167 | 926 | 1075 | 25 | 11/EM/0398 | A Phase III, Multi-center, Double-Blind, Randomized, Placebo Controlled Clinical Trial to Evaluate the Safety and Efficacy of MK0431A (A Fixed-Dose Combination Tablet of Sitagliptin and Metformin) in Pediatric Patients with Type 2 Diabetes Mellitus) | Available | 1 | Available | 2017-12-03 | Open | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34168 | 926 | 1075 | 25 | 14/ES/0001 | Randomised, Double-Blind, Placebo-Controlled, Parallel-Group Study to Assess Cardiovascular Outcomes Following Treatment with Ertugliflozin (MK-8835/PF-04971729) in Participants with Type 2 Diabetes | Available | 10 | Available | 2015-09-30 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34169 | 926 | 1075 | 25 | 14/YH/0088 | Phase I study of KHK2823 in AML or MDS | Available | 8 | Available | 2017-07-01 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34170 | 926 | 1075 | 25 | 13/NE/0126 | ASSIGN NEO.1.C/F | Available | 2 | Available | 2014-12-31 | Open | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34171 | 926 | 1075 | 25 | 13/WA/0413 | EORTC 40085 | Available | 4 | Available | 2015-02-15 | In set up | N/A | Sit not active | Unknown | Unknown | 2014-10-20 | 2014-10-29
34172 | 926 | 1075 | 25 | 14/LO/0667 | MK5172/MK8742 in Subjects with HCV/HIV Co-Infection | Available | 11 | Available | 2014-07-31 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34173 | 926 | 1075 | 25 | 13/EM/0154 | SWIFFT | Available | 20 | Available | 2016-03-31 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34174 | 926 | 1075 | 25 | 14/WM/0135 | Daratumumab+Rd vs Rd in Relapsed or Refractory Multiple Myeloma | Available | 5 | Available | 2020-03-27 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34369 | 926 | 1075 | 25 | 14/LO/0602 | An OpenLabel, Multicenter Evaluation of the Safety and Efficacy of Recombinant Coagulation Factor IX Fc Fusion Protein (rFIXFc; BIIB029) in the Prevention and Treatment of Bleeding in Previously Untreated Patients With Severe Hemophilia B | Available | 4 | Available | 2022-12-01 | In set up | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34370 | 926 | 1075 | 25 | 14/YH/1057 | A phase 3, multicenter, randomized, open-label study to compare the efficasy and safety of sofosbuvir/ GS-5816 fixed dose combination for 12 weeks with sofosbuvir and ribavirin for 24 weeks in subjects with chronic genotype 3 HCV Infection | Available | 9 | Available | 2015-02-01 | Open | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34371 | 926 | 1075 | 25 | 14/WM/1056 | A Phase 3, Multicenter, Randomized, DoubleBlind, Placebo Controlled Study to Investigate the Efficacy and Safety of Sofosbuvir/GS5816 Fixed Dose Combination for 12 Weeks in Subjects with Chronic HCV | Available | 8 | No Date Agreed With Sponsor |  | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34372 | 926 | 1075 | 25 | 13/SC/0111 | FOCUS4: Molecular selection of therapy in colorectal cancer | Available | 34 | Available | 2017-11-30 | In set up | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34373 | 926 | 1075 | 25 | 12/LO/1889 | FTY720 in Primary Progressive Multiple Sclerosis Open Label Extension | Available | 7 | Available | 2014-08-06 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34374 | 926 | 1075 | 25 | 14/SC/0170 | Phase 3 study to test the effects of SA237 in patients with NMO&NMOSD SA-307JG | Available | 4 | Available | 2015-01-30 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34375 | 926 | 1075 | 25 | 14/YH/0090 | Study to test ADIPEG20 in patients with mesothelioma and NSCLC V 02 | Available | 47 | Available | 2016-01-01 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34376 | 926 | 1075 | 25 | 14/LO/0680 | MEDI4736 in NSCLC (D4191C00003, ATLANTIC Study) | Available | 5 | Available | 2016-02-01 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34377 | 926 | 1075 | 25 | 14/LO/1042 | GO29293 AntiPDL1 | Available | 2 | Available | 2015-11-22 | Closed - Follow Up Complete | Y |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34378 | 926 | 1075 | 25 | 13/LO/1682 | Study of Maintenance Rucaparib in Relapsed Highgrade | Available | 6 | Available | 2016-12-31 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29
34379 | 926 | 1075 | 25 | 13/LO/1595 | CBT vs Standardised Medical Care to treat Dissociative Seizures | Available | 10 | Available | 2016-12-31 | Open | N/A |  | Unknown | Unknown | 2014-10-20 | 2014-10-29