## Sheet1
2016-17 Q4 Project Intiation Report
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Reasons for delay correspond to:
98498 | 14/YH/0085 | 126738 | NHS Permission | FLAIR version 1.0 | 2016-03-14 | 2016-04-05 | No |  | 22 | [5 empty] | No | [5 empty] | Please Select... |  | F - No patients seen | Neither
98499 | 14/WS/1113 | 153352 | NHS Permission | 3562 CAPE Study Version 1.0 | 2016-04-01 | 2016-06-17 | Yes | 2016-08-31 | 77 | 75 | 152 |  |  |  | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98500 | 15/LO/1549 | 169718 | NHS Permission | Pre-PRO | 2016-03-18 | 2016-04-19 | Yes | 2016-05-03 | 32 | 14 | 46 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98501 | 14/WM/1260 | 163072 | NHS Permission | PHAZAR | 2016-03-30 | 2016-04-14 | No |  | 15 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98502 | 15/SC/0640 | 178883 | NHS Permission | Calypso | 2016-03-30 | 2016-05-04 | Yes | 2016-05-05 | 35 | 1 | 36 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98503 | 15/YH/0004 | 167453 | NHS Permission | ARIOS: Follow-up of infants born to mothers with in retosiban studies | 2016-03-30 | 2016-05-11 | No |  | 42 | [5 empty] | No | [5 empty] | Please Select... |  | F - No patients seen | Sponsor
98504 | 15/YH/0003 | 167451 | NHS Permission | ZINN: Retosiban versus atosiban for spontaneous preterm | 2016-03-30 | 2016-05-09 | No |  | 40 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98505 | 15/LO/0040 | 155632 | NHS Permission | Evaluate effect of GS6615 on Exercise capacity in subjects with HCM | 2016-03-27 | 2016-04-26 | No |  | 30 | [5 empty] | No | [5 empty] | Please Select... |  | J - Other | Neither
98506 | 15/LO/1906 | 192701 | NHS Permission | A Randomised, Double-Blind, Placebo-Controlled Trial of the Safety | 2016-03-29 | 2016-04-22 | Yes | 2016-08-12 | 24 | 112 | 136 |  |  |  | No | [5 empty] | Please Select... |  | J - Other | Neither
98507 | 15/LO/2134 | 188448 | NHS Permission | Predictors 5.1 | 2016-02-24 | 2016-04-13 | Yes | 2016-04-22 | 49 | 9 | 58 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98508 | 16/LO/0029 | 195696 | NHS Permission | Phase 3 study with GS-9883/F/TAF in HIV-1, treatment na?ve subjects | 2016-03-23 | 2016-04-05 | Yes | 2016-04-14 | 13 | 9 | 22 |  |  |  | Yes | [5 empty] | Please Select... |  | H - Contracting delays | Please Select...
98509 | 15/LO/1908 | 184768 | NHS Permission | Phase I/IIa Study of DTP3 in Patients With Advanced Multiple Myeloma | 2016-03-15 | 2016-04-18 | No |  | 34 | [5 empty] | No | [5 empty] | Please Select... |  | F - No patients seen | Neither
98510 | 16/LO/0022 | 195532 | NHS Permission | Phase 1 BAX 826 Dose-Escalation Safety Study, Protocol 291501 | 2016-03-23 | 2016-05-24 | No |  | 62 | [5 empty] | No | [5 empty] | Please Select... |  | H - Contracting delays | Sponsor
98511 | 16/LO/0304 | 199075 | NHS Permission | VELOCITY | 2016-03-28 | 2016-04-18 | Yes | 2016-04-19 | 21 | 1 | 22 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98512 | 16/LO/0036 | 195359 | NHS Permission | GS-9883/F/TAF versus ABC/DTG/3TC in HIV-1, treatment-naive subjects | 2016-03-03 | 2016-04-01 | Yes | 2016-04-26 | 29 | 25 | 54 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98513 | 15/LO/1879 | 186859 | NHS Permission | A Randomized, Open-Label Study of Ponatinib Versus Nilotinib in Patients with Chronic Myeloid Leukem | 2016-03-23 | 2016-04-01 | No |  | 9 | [5 empty] | No | [5 empty] | Please Select... |  | F - No patients seen | Neither
98514 | 16/EM/0133 | 184873 | NHS Permission | CAIN457H2315 | 2016-04-08 | 2016-06-08 | Yes | 2016-06-20 | 61 | 12 | 73 |  |  |  | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98515 | 15/WM/0268 | 180518 | NHS Permission | ENRICH | 2016-03-07 | 2016-04-05 | No |  | 29 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98516 | 15/LO/2124 | 192795 | NHS Permission | The ?METRIC? Study | 2016-03-23 | 2016-04-08 | Yes | 2016-05-13 | 16 | 35 | 51 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98517 | 15/YH/0530 | 886569 | NHS Permission | CLARITY | 2016-03-15 | 2016-04-12 | No |  | 28 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98518 | 16/NW/0071 | 195362 | NHS Permission | Pelle-926-201- Double- Blind, Randomized, Vehicle-Controlled Proof of Concept Clinical Trial | 2016-03-29 | 2016-04-18 | Yes | 2016-06-07 | 20 | 50 | 70 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98519 | 16/LO/0026 | 195795 | NHS Permission | Phase 3 open-label switch study with GS-9883/F/TAF in HIV-1 subjects | 2016-03-23 | 2016-04-20 | Yes | 2016-05-17 | 28 | 27 | 55 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98520 | 16/ES/0001 | 193859 | NHS Permission | GED 0301 CD 002 PhIII study for subjects with Active Crohns Disease | 2016-03-31 | 2016-04-20 | No |  | 20 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98521 | 16/LO/0152 | 193306 | NHS Permission | Evaluate the Effect of a Digital Disease Management Tool in DM Patient | 2016-03-22 | 2016-04-21 | Yes | 2016-05-27 | 30 | 36 | 66 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98522 | 15/LO/1876 | 184353 | NHS Permission | A Phase 2, Randomized, Double-Blind, Placebo-Controlled, Parallel Group, Multi-Center Study | 2016-03-28 | 2016-04-26 | Yes | 2016-07-21 | 29 | 86 | 115 |  |  |  | No | [5 empty] | Please Select... |  | G - No patients consented | Sponsor
98523 | 16/WS/0077 | 202213 | NHS Permission | (duplicate) M10-870 Adalimumab in Paediatric Ulcerative Colitis (Ext) | 2016-05-03 | 2016-05-03 | Yes | 2016-06-01 | 0 | 29 | 29 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98524 | 15/LO/1945 | 184624 | NHS Permission | Prophylaxis against acute attacks of Hereditary Angioedema (HAE) | 2016-03-26 | 2016-05-04 | Yes | 2016-05-25 | 39 | 21 | 60 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98525 | 15/LO/2034 | 190228 | NHS Permission | A Phase 1b Study to Evaluate safety and clinical activity of Pembrolizumab (MK3475) in combination | 2016-03-29 | 2016-05-04 | No |  | 36 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98526 | 16/LO/0092 | 194133 | NHS Permission | A PHASE Ib/II STUDY EVALUATING THE SAFETY AND EFFICACY OF OBINUTUZUMAB IN COMBINATION WITH POLATUZUM | 2016-03-23 | 2016-05-09 | No |  | 47 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98527 | 15/LO/1077 | 173350 | NHS Permission | ABC-07 | 2016-03-17 | 2016-05-09 | No |  | 53 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98528 | 11/SS/0100 | 84669 | NHS Permission | Fluoxetine Or Control Under Supervision (FOCUS) | 2016-02-29 | 2016-05-09 | No |  | 70 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98529 | 15/EE/0464 | 183877 | NHS Permission | LJPC-501 in Patients with Catecholamine-Resistant Hypotension | 2016-03-23 | 2016-05-16 | No |  | 54 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98530 | 14/YH/1199 | 153953 | NHS Permission | GALACTIC | 2016-03-10 | 2016-05-23 | No |  | 74 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98531 | 15/SS/0194 | 173717 | NHS Permission | A multicentre 52 week double blind Asthma study with QMF149 | 2016-04-11 | 2016-05-19 | Yes | 2016-06-10 | 38 | 22 | 60 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98532 | 13/LO/1616 | 137039 | NHS Permission | NCRN - 2888 MEDI4736 in Advanced Solid Tumors | 2016-03-22 | 2016-05-19 | Yes | 2016-05-24 | 58 | 5 | 63 |  |  |  | Yes | [5 empty] | Please Select... |  |  | Please Select...
98533 | 14/SC/0171 | 120104 | NHS Permission | Add-Aspirin | 2016-03-11 | 2016-06-08 | No |  | 89 | [5 empty] | No | [5 empty] | Please Select... |  | H - Contracting delays | Sponsor
98534 | 15/EM/0422 | 187040 | NHS Permission | BAX69 | 2016-03-23 | 2016-05-25 | No |  | 63 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98535 | 13/ES/0123 | 119188 | NHS Permission | NiCCC Trial (BIBF1120) | 2016-03-21 | 2016-06-01 | No |  | 72 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98536 | 16/WA/0060 | 195792 | NHS Permission | Idasanutlin in relapsed/refractory AML | 2016-03-15 | 2016-06-13 | Yes | 2016-08-30 | 90 | 78 | 168 |  |  |  | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98537 | 14/NW/1488 | 164229 | NHS Permission | AD4833/TOMM40_303 Extension Alzheimer's Disease study | 2016-03-22 | 2016-06-29 | No |  | 99 | [5 empty] | No | [5 empty] | Please Select... |  | H - Contracting delays | Sponsor
98538 | 14/NW/1219 | 160371 | NHS Permission | NERVES | 2016-03-31 | 2016-08-05 | No |  | 127 | [5 empty] | No | [5 empty] | Please Select... |  | A - Permissions delayed/denied | Neither
98539 | 15/NW/0592 | 185435 | NHS Permission | DIAB 3796 | 2015-12-04 | 2016-07-01 | No |  | 210 | [5 empty] | No | [5 empty] | Please Select... |  | F - No patients seen | Sponsor
98540 | 16/LO/0677 | 190078 | HRA Approval | A multicenter, randomized, 52-week, double-blind, parallelgroup, active controlled study to compare |  |  | Yes | 2016-09-22 |  |  |  | 99 | 55 | 154 | No |  | 2016-04-21 | 2016-06-16 | 2016-06-12 | 2016-07-29 | Please Select... | 2016-08-18 | D - Sponsor Delays | Sponsor
98541 | 16/WM/0197 | 202991 | HRA Approval | RO5459072 in Primary Sjogren's Syndrome |  |  | No |  |  |  |  | 105 |  |  | No |  | 2016-04-28 | 2016-07-07 | 2016-07-19 | 2016-08-11 | Please Select... | 2016-09-19 | A - Permissions delayed/denied | Sponsor
98542 | 16/LO/0582 | 191697 | HRA Approval | C31005 MLN0128 and MLN0128+MLN117 Compared With Everolimus in mccRCC |  |  | No |  |  |  |  | 437 |  |  | No |  | 2016-05-17 | 2016-06-23 | 2016-07-26 | 2017-07-28 | Please Select... | 2016-09-28 | D - Sponsor Delays | Sponsor
98543 | 16/LO/0919 | 201803 | HRA Approval | MEDI4736 with Tremelimumab in advanced solid tumours |  |  | No |  |  |  |  | 116 |  |  | No |  | 2016-05-16 | 2016-07-13 | 2016-08-30 | 2016-09-09 | Please Select... |  | A - Permissions delayed/denied | Neither
98544 | 14/WA/1118 | 159836 | NHS Permission | Postoperative adjuvant treatment for HPV positive tumours (PATHOS) | 2016-03-21 | 2016-07-05 | No |  | 106 | [5 empty] | No | [5 empty] | Please Select... |  | A - Permissions delayed/denied | Both
98545 | 16/LO/0877 | 202257 | HRA Approval | A PHASE 3, MULTICENTER, MULTINATIONAL, RANDOMIZED, OPEN-LABEL, PARALLEL-ARM STUDY OF AVELUMAB*(MSB00 |  |  | Yes | 2016-10-18 |  |  |  | 16 | 39 | 55 | Yes |  | 2016-08-24 | 2016-09-05 | 2016-09-06 | 2016-09-09 | Please Select... |  |  | Please Select...
98546 | 16/EM/0193 | 190690 | HRA Approval | The dal-GenE trial |  |  | No |  |  |  |  | 87 |  |  | No |  | 2016-06-14 | 2016-06-14 | 2016-09-01 | 2016-09-09 | Please Select... | 2016-09-27 | A - Permissions delayed/denied | Neither
98547 | 16/NE/0147 | 204478 | HRA Approval | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Phase III Study to Evaluate the Efficacy |  |  | No |  |  |  |  | 80 |  |  | No |  | 2016-06-03 | 2016-06-15 | 2016-08-18 | 2016-08-22 | Please Select... | 2016-09-05 | H - Contracting delays | Sponsor
98548 | 16/NE/0121 | 196233 | HRA Approval | SEM200-008 Study |  |  | Yes | 2016-09-14 |  |  |  | 69 | 23 | 92 | No |  | 2016-06-14 | 2016-06-08 | 2016-07-29 | 2016-08-22 | Please Select... | 2016-08-25 | D - Sponsor Delays | Sponsor
98549 | 15/EM/0440 | 178108 | NHS Permission | AZTEC | 2016-03-15 | 2016-07-21 | No |  | 128 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Sponsor
98550 | 16/LO/1060 | 202362 | HRA Approval | EXPEDITION-2 |  |  | Yes | 2016-08-08 |  |  |  | 24 | 10 | 34 | Yes |  | 2016-07-05 | 2016-07-12 | 2016-07-25 | 2016-07-29 | Please Select... | 2016-08-01 |  | Please Select...
98551 | 16/NW/0253 | 188110 | HRA Approval | M13-542 Phase 3 ABT-494 |  |  | Yes | 2016-09-20 |  |  |  | 104 | 21 | 125 | No |  | 2016-05-18 | 2016-08-10 | 2016-07-18 | 2016-08-30 | Please Select... | 2016-09-06 | A - Permissions delayed/denied | Neither
98552 | 15/LO/1760 | 184374 | NHS Permission | BISCAY | 2016-03-23 | 2016-07-19 | Yes | 2016-08-04 | 118 | 16 | 134 |  |  |  | No | [5 empty] | Please Select... |  | A - Permissions delayed/denied | Neither
98553 | 16/SC/0068 | 196245 | NHS Permission | MEDI4736 | 2016-03-29 | 2016-07-20 | Yes | 2016-08-31 | 113 | 42 | 155 |  |  |  | No | [5 empty] | Please Select... |  | A - Permissions delayed/denied | Neither
98554 | 15/SS/0107 | 173327 | NHS Permission | SPARE | 2016-03-30 | 2016-07-25 | No |  | 117 | [5 empty] | No | [5 empty] | Please Select... |  | D - Sponsor Delays | Both
98555 | 16/NS/0070 | 208445 | HRA Approval | The HeartFlow ADVANCE Registry |  |  | Yes | 2016-10-20 |  |  |  | 50 | 34 | 84 | No |  | 2016-07-28 | 2016-07-22 | 2016-05-09 | 2016-09-16 | Please Select... | 2016-10-12 | D - Sponsor Delays | Sponsor
98556 | 16/NW/0506 | 207353 | HRA Approval | Achilles |  |  | No |  |  |  |  | 58 |  |  | No |  | 2016-07-12 | 2016-08-24 | 2016-08-22 | 2016-09-08 | Please Select... | 2016-09-08 | F - No patients seen | Neither
98557 | 16/LO/0498 | 196286 | NHS Permission | NAVIGATE | 2016-04-04 | 2016-08-23 | Yes | 2016-09-14 | 141 | 22 | 163 |  |  |  | No | [5 empty] | Please Select... |  | A - Permissions delayed/denied | Sponsor
98558 | 16/LO/1113 | 209455 | HRA Approval | A Phase III, randomised, double-blind, multicentre, parallel-group, non-inferiority study evaluating the efficacy, safety, and tolerability of dolutegravir plus lamivudine compared to dolutegravir plus tenofovir/emtricitabine in HIV-1-infected treatment-naïve adults |  |  | Yes | 2016-11-03 |  |  |  | 96 | 30 | 126 | No |  | 2016-06-30 | 2016-09-12 | 2016-09-28 | 2016-10-04 | Please Select... |  | A - Permissions delayed/denied | Neither
98559 | 16/LO/1379 | 183308 | HRA Approval | STAR MAPPING |  |  | Yes | 2016-10-13 |  |  |  | 51 | 7 | 58 | Yes |  | 2016-08-16 | 2016-09-23 | 2016-10-06 | 2016-10-06 | Please Select... | 2016-10-06 |  | Please Select...
98560 | 16/LO/1022 | 206466 | HRA Approval | FUSION MM-003 |  |  | No |  |  |  |  | 66 |  |  | No |  | 2016-08-02 | 2016-07-27 | 2016-09-22 | 2016-10-07 | Please Select... | 2016-10-20 | D - Sponsor Delays | Neither
98561 | 16/LO/0952 | 188893 | HRA Approval | An open-label, multicentre, international pilot study of paritaprevir/ritonavir, ombitasvir, dasabuvir with or without ribavirin for people with recently acquired hepatitis C virus infection with or without HIV co-infection. |  |  | Yes | 2016-10-25 |  |  |  | 56 | 13 | 69 | Yes |  | 2016-08-17 | 2016-08-01 | 2016-09-23 | 2016-10-12 | Please Select... | 2016-10-24 |  | Please Select...
98562 | 16/LO/1457 | 199790 | HRA Approval | AILD (VTL 308) |  |  | No |  |  |  |  | 50 |  |  | No |  | 2016-08-25 | 2016-10-12 | 2016-09-26 | 2016-10-14 | Please Select... | 2016-10-14 | D - Sponsor Delays | Neither
98563 | 16/LO/0858 | 205417 | HRA Approval | A randomized, double-blind, placebo-controlled, dose-ranging, parallel-group study to evaluate the efficacy, safety, tolerability, pharmacokinetics and pharmacodynamics of BCX7353 as a preventative treatment to reduce the frequency of attacks in subjects with hereditary angioedema |  |  | Yes | 2016-11-01 |  |  |  | 77 | 12 | 89 | No |  | 2016-08-04 | 2016-08-03 | 2016-07-15 | 2016-10-20 | Please Select... | 2016-10-24 | D - Sponsor Delays | Sponsor
98564 | 16/LO/1106 | 207909 | HRA Approval | KEYTONE-355 |  |  | No |  |  |  |  | 78 |  |  | No |  | 2016-08-04 | 2016-08-15 | 2016-10-18 | 2016-10-21 | Please Select... | 2016-11-24 | D - Sponsor Delays | Sponsor
98565 | 16/LO/0574 | 150998 | HRA Approval | Phase I/II, First in Human, Dose Escalation Trial of the Bruton’s Tyrosine Kinase Inhibitor M7583 in Patients with Relapsed/Refractory B Cell Malignancies and Expansion Cohorts in Patients with Mantle Cell Lymphoma and Diffuse Large B Cell Lymphoma (ABC subtype) that have Progressed after at least 1 but not more than 3 Prior Lines of Therapy |  |  | No |  |  |  |  | 126 |  |  | No |  | 2016-06-30 | 2016-07-06 | 2016-10-14 | 2016-11-03 | Please Select... | 2016-11-03 | D - Sponsor Delays | Sponsor
98566 | 16/YH/0376 | 201698 | HRA Approval | A Prospective Randomized Placebo Controlled Study to Evaluate the Effect of Celecoxib on the Efficacy and Safety of Amlodipine on Renal and Vascular Function in Subjects with Existing Hypertension Requiring Antihypertensive Therapy |  |  | No |  |  |  |  | 43 |  |  | No |  | 2016-10-05 | 2016-10-10 | 2016-10-14 | 2016-11-17 | Please Select... |  | D - Sponsor Delays | Sponsor
98567 | 16/SW/0090 | 199970 | HRA Approval | A Phase 3, Multicentre, Randomised, Double-blind, Placebo-controlled Study Evaluating the Efficacy and Safety of Ustekinumab in the Treatment of Anti-TNFÎ± Refractory Subjects With Active Radiographic Axial Spondyloarthritis |  |  | Yes | 2016-11-29 |  |  |  | 221 | 7 | 228 | No |  | 2016-04-15 | 2016-06-23 | 2016-11-17 | 2016-11-22 | Please Select... | 2016-11-22 | H - Contracting delays | Sponsor
98568 | 16/LO/1181 | 206679 | HRA Approval | "A Phase 2 a randomized, double-blind, placebo-controlled trial of MHAA4549A, a monoclonal antibody, administered as monotherapy for the treatment of acute uncomplicated seasonal influenza A infection in otherwise healthy adults" |  |  | No |  |  |  |  | 76 |  |  | No |  | 2016-09-07 | 2016-09-28 | 2016-11-14 | 2016-11-22 | Please Select... | 2016-12-06 | D - Sponsor Delays | Sponsor
98569 | 14/LO/2033 | 145427 | HRA Approval | PROVENT |  |  | Yes | 2016-12-15 |  |  |  | 11 | 9 | 20 | Yes |  | 2016-11-25 | 2016-08-17 | 2016-12-06 | 2016-12-06 | Please Select... | 2016-12-08 |  | Please Select...
98570 | 16/LO/0019 | 180161 | HRA Approval | Bone Evaluation in women over 40 who Switch from Truvada/NNRTI to Triumeq |  |  | No |  |  |  |  | 99 |  |  | No |  | 2016-08-23 | 2016-06-15 | 2016-11-21 | 2016-11-30 | Please Select... |  | D - Sponsor Delays | Sponsor
98571 | 16/LO/1124 | 199447 | HRA Approval | LOXO-TRK 15002 |  |  | No |  |  |  |  | 12 |  |  | No |  | 2016-11-21 | 2016-11-18 | 2016-11-29 | 2016-12-03 | Please Select... | 2016-12-13 | D - Sponsor Delays | Sponsor
98572 | 16/NE/0175 | 203823 | HRA Approval | A Phase 2/3 Multicentre, Open-label, 3-arm, 2-stage Randomised Study of ASP2215 (Gilteritinib), Combination of ASP2215 Plus Azacitidine and Azacitidine Alone in the Treatment of Newly Diagnosed Acute Myeloid Leukaemia with FLT3 Mutation in Patients Not Eligible for Intensive Induction Chemotherapy. |  |  | No |  |  |  |  | 7 |  |  | No |  | 2016-12-01 | 2016-12-01 | 2016-11-23 | 2016-12-08 | Please Select... |  | D - Sponsor Delays | Sponsor
98573 | 16/LO/1697 | 212844 | HRA Approval | A Phase III Randomized, Controlled Clinical Trial of Pembrolizumab with or without Platinum-Based Combination Chemotherapy versus Chemotherapy in Subjects with Advanced or Metastatic Urothelial Carcinoma |  |  | Yes | 2016-12-13 |  |  |  | 49 | 11 | 60 | Yes |  | 2016-10-14 | 2016-11-11 | 2016-11-28 | 2016-12-02 | Please Select... | 2016-12-12 |  | Please Select...
98574 | 16/YH0438 | 208755 | HRA Approval | Prebiotic effect on markers of peripheral immunity and inflammation in gastrointestinal inflammation |  |  | No |  |  |  |  | 24 |  |  | No |  | 2016-11-11 | 2016-11-08 | 2016-12-02 | 2016-12-05 | Please Select... | 2016-12-05 | D - Sponsor Delays | Sponsor
102375 | 14/SS/1031 | 159610 | HRA Approval | STOPPIT-2 |  |  | No |  |  |  |  | 21 |  |  | Within 70 Days |  | 2017-02-15 | 2016-05-20 | 2017-02-15 | 2017-03-08 | Please Select... |  | D - Sponsor Delays | Neither
102376 | 16/LO/1271 | 178683 | HRA Approval | MODS |  |  | No |  |  |  |  | 27 |  |  | Within 70 Days |  | 2017-02-22 | 2017-01-13 | 2017-03-14 | 2017-03-21 | Please Select... |  | D - Sponsor Delays | Neither
102377 | 16/LO/1854 | 184654 | HRA Approval | Discover |  |  | Yes | 2017-01-30 |  |  |  | 101 | 14 | 115 | No |  | 2016-10-07 | 2016-12-14 | 2017-01-04 | 2017-01-16 | Please Select... | 2017-01-16 | D - Sponsor Delays | Sponsor
102378 | 16/LO/1318 | 187932 | HRA Approval | Nucleos(t)ide withdrawal in Hepatitis B virus infection (NUC-B) |  |  | No |  |  |  |  | 110 |  |  | No |  | 2016-09-29 | 2016-09-21 | 2016-12-15 | 2017-01-17 | Please Select... | 2017-01-23 | D - Sponsor Delays | Sponsor
102379 | 16/NW/0517 | 188554 | HRA Approval | Myeloma XII (ACCoRd trial) Version 1.0 |  |  | Yes | 2017-03-28 |  |  |  | 1 | 12 | 13 | Yes |  | 2017-03-15 | 2016-10-27 | 2016-08-01 | 2017-03-16 | Please Select... | 2017-03-20 |  | Please Select...
102380 | 16/SS/0074 | 196616 | HRA Approval | The IPED study |  |  | Yes | 2017-03-01 |  |  |  | 35 | 19 | 54 | Yes |  | 2017-01-06 | 2016-12-28 | 2017-01-06 | 2017-02-10 | Please Select... | 2017-02-27 |  | Please Select...
102381 | 16/WS/0068 | 199202 | HRA Approval | Quantitative Fibronectin to help Decision-making in women with Symptoms of Preterm Labour ('QUIDS') |  |  | Yes | 2017-03-29 |  |  |  | 68 | 37 | 105 | No |  | 2016-12-14 | 2016-07-13 | 2016-12-22 | 2017-02-20 | Please Select... | 2017-03-22 | D - Sponsor Delays | Sponsor
102382 | 16/EE/0294 | 199550 | HRA Approval | AIM HY-INFORM |  |  | Yes | 2017-02-20 |  |  |  | 42 | 20 | 62 | Yes |  | 2016-12-20 | 2016-11-01 | 2016-11-28 | 2017-01-31 | Please Select... | 2017-02-01 |  | Please Select...
102383 | 16/EM/0198 | 199630 | HRA Approval | GO30081 (IMPower-133) |  |  | Yes | 2017-03-08 |  |  |  | 86 | 41 | 127 | No |  | 2016-11-01 | 2016-10-03 | 2016-12-14 | 2017-01-26 | Please Select... | 2017-02-28 | D - Sponsor Delays | Both
102384 | 16/SC/0231 | 201464 | HRA Approval | AG-120/AG-221 plus azacitidine in treatment of IDH1/IDH2 AML |  |  | No |  |  |  |  | 57 |  |  | No |  | 2017-01-16 | 2016-09-23 | 2017-03-09 | 2017-03-14 | Please Select... |  | D - Sponsor Delays | Sponsor
102467 | 16/LO/1781 | 203431 | HRA Approval | LUTONIX Global AV Registry |  |  | Yes | 2017-03-04 |  |  |  | 65 | 1 | 66 | Yes |  | 2016-12-28 | 2016-11-09 | 2017-02-22 | 2017-03-03 | Please Select... | 2017-03-03 |  | Please Select...
102468 | 16/LO/0769 | 204758 | HRA Approval | MSB0011359C in solid tumours (EMR 200647-001) |  |  | No |  |  |  |  | 51 |  |  | No |  | 2016-11-21 | 2016-12-06 | 2016-11-23 | 2017-01-11 | Please Select... |  | D - Sponsor Delays | Sponsor
102469 | 16/SC/0454 | 206701 | HRA Approval | SHP626-201 Volixibat in Adults with Nonalcoholic Steatohepatitis |  |  | No |  |  |  |  | 140 |  |  | No |  | 2016-10-12 | 2016-11-15 | 2017-02-13 | 2017-03-01 | Please Select... |  | D - Sponsor Delays | Sponsor
102470 | 16/NW/0620 | 206738 | HRA Approval | Pro2tect-Correction |  |  | No |  |  |  |  | 11 |  |  | Within 70 Days |  | 2017-03-09 | 2017-03-07 | 2017-03-20 | 2017-03-20 | Please Select... |  | D - Sponsor Delays | Sponsor
102471 | 16/NW/0621 | 206740 | HRA Approval | Pro2tect-Conversion |  |  | No |  |  |  |  | 11 |  |  | Within 70 Days |  | 2017-03-09 | 2016-10-21 | 2017-03-20 | 2017-03-20 | Please Select... |  | D - Sponsor Delays | Sponsor
102472 | 16/LO/1211 | 207428 | HRA Approval | JHL-CLIN-1101-01: JHL1101 versus MabThera in RA |  |  | No |  |  |  |  | 13 |  |  | Within 70 Days |  | 2017-02-21 | 2016-08-25 | 2016-11-17 | 2017-03-06 | Please Select... |  | D - Sponsor Delays | Sponsor
102473 | 16-WUS-0187 | 207686 | HRA Approval | PRESSUREwire |  |  | Yes | 2017-03-27 |  |  |  | 90 | 19 | 109 | No |  | 2016-12-08 | 2016-12-21 | 2017-02-13 | 2017-03-08 | Please Select... | 2017-03-24 | D - Sponsor Delays | Both
102474 | 16/EM/0320 | 208246 | HRA Approval | KATE-2 |  |  | No |  |  |  |  | 156 |  |  | No |  | 2016-09-21 | 2016-11-15 | 2016-12-07 | 2017-02-24 | Please Select... | 2017-03-01 | H - Contracting delays | Both
102475 | 16/LO/2067 | 209688 | HRA Approval | Optimisation of Peri-operative Cardiovascular Management to Improve Surgical Outcome II (Optimise II) Trial |  |  | Yes | 2017-01-26 |  |  |  | 31 | 13 | 44 | Yes |  | 2016-12-13 | 2017-01-06 | 2016-09-22 | 2017-01-13 | Please Select... | 2017-01-02 |  | Please Select...
102476 | 16/LO/1810 | 209789 | HRA Approval | UTX-TGR-304 |  |  | No |  |  |  |  | 98 |  |  | No |  | 2016-10-24 | 2017-01-03 | 2017-01-18 | 2017-01-30 | Please Select... | 2017-03-08 | D - Sponsor Delays | Sponsor
102512 | 16/WM/0396 | 210511 | HRA Approval | RENA 4591 |  |  | No |  |  |  |  | 68 |  |  | No |  | 2016-12-28 | 2017-02-03 | 2017-02-17 | 2017-03-06 | Please Select... |  | D - Sponsor Delays | Sponsor
102513 | 16/LO/1511 | 210799 | HRA Approval | Evaluation of the Clinical Performance of Alere HBsAg |  |  | Yes | 2017-02-15 |  |  |  | 73 | 19 | 92 | No |  | 2016-11-15 | 2016-11-02 | 2017-01-25 | 2017-01-27 | Please Select... | 2017-01-27 | D - Sponsor Delays | Sponsor
102514 | 16/LO/1648 | 210861 | HRA Approval | CANC 30364 (MK-3475-426) |  |  | Yes | 2017-01-25 |  |  |  | 105 | 14 | 119 | No |  | 2016-09-28 | 2016-12-19 | 2016-11-28 | 2017-01-11 | Please Select... | 2017-01-12 | A - Permissions delayed/denied | Neither
102515 | 16/EM/0408 | 211983 | HRA Approval | A Phase 2, Open-Label, Randomized Study to Evaluate the Efficacy and Safety of GS-5745 Combined with Nivolumab versus Nivolumab Alone in Subjects with Unresectable or Recurrent Gastric or Gastroesophageal Junction Adenocarcinoma |  |  | No |  |  |  |  | 124 |  |  | No |  | 2016-10-05 | 2016-12-02 | 2017-01-26 | 2017-02-06 | Please Select... | 2017-02-21 | D - Sponsor Delays | Sponsor
102516 | 16/YH/0424 | 212539 | HRA Approval | RADIANCE |  |  | Yes | 2017-02-23 |  |  |  | 85 | 21 | 106 | No |  | 2016-11-09 | 2017-01-27 | 2017-01-26 | 2017-02-02 | Please Select... | 2017-02-03 | D - Sponsor Delays | Sponsor
102517 | 16/LO/1822 | 212944 | HRA Approval | CARD 5650 |  |  | No |  |  |  |  | 97 |  |  | No |  | 2016-10-12 | 2016-12-07 | 2017-01-11 | 2017-01-17 | Please Select... | 2017-01-17 | D - Sponsor Delays | Sponsor
102518 | 16/LO/1940 | 213099 | HRA Approval | SAUL |  |  | Yes | 2017-02-23 |  |  |  | 100 | 28 | 128 | No |  | 2016-10-18 | 2017-01-12 | 2017-01-16 | 2017-01-26 | Please Select... | 2017-02-09 | D - Sponsor Delays | Sponsor
102528 | 16/EM/0436 | 213166 | HRA Approval | ALXN1210-aHUS-311 |  |  | No |  |  |  |  | 74 |  |  | No |  | 2016-12-01 | 2016-12-07 | 2017-01-23 | 2017-02-13 | Please Select... |  | D - Sponsor Delays | Sponsor
102529 | 16/LO/2078 | 213487 | HRA Approval | Roche RO674281/Trastuzumab/Cetuximab/Obinutuzumab (BP29842) |  |  | No |  |  |  |  | 73 |  |  | No |  | 2016-12-09 | 2017-02-03 | 2017-02-08 | 2017-02-20 | Please Select... | 2017-03-24 | D - Sponsor Delays | Sponsor
102530 | 16/LO/1891 | 213918 | HRA Approval | Phase 2 Study of GS-4997 with Prednisolone vs Prednisolone alone in AH |  |  | No |  |  |  |  | 112 |  |  | No |  | 2016-11-16 | 2017-01-09 | 2017-02-13 | 2017-03-08 | Please Select... | 2017-03-09 | D - Sponsor Delays | Sponsor
102531 | 16/SC/0548 | 215022 | HRA Approval | Auriel-RA |  |  | Yes | 2017-03-28 |  |  |  | 16 | 26 | 42 | Yes |  | 2017-02-14 | 2017-02-14 | 2017-02-22 | 2017-03-02 | Please Select... | 2017-03-06 |  | Please Select...
102532 | 16/LO/1984 | 215378 | HRA Approval | MK-3682 + MK-8408 for 12 weeks in Subjects with HCV GT1-6 Infection |  |  | Yes | 2017-02-16 |  |  |  | 83 | 10 | 93 | No |  | 2016-11-15 | 2017-01-06 | 2017-01-30 | 2017-02-06 | Please Select... | 2017-02-06 | D - Sponsor Delays | Sponsor
102533 | 16/NE/0415 | 217915 | HRA Approval | Phase 2a Study of AL-335, Odalasvir, with/without Simeprevir for Hep C |  |  | No |  |  |  |  | 84 |  |  | No |  | 2016-12-14 | 2017-02-28 | 2017-02-14 | 2017-03-08 | Please Select... |  | A - Permissions delayed/denied | Neither
102534 | 16/WM/0507 | 218607 | HRA Approval | CAIN457F2366 (EXCEED 1) Secukinumab compared with Adalimumab in PsA |  |  | No |  |  |  |  | 22 |  |  | Within 70 Days |  | 2017-03-02 | 2017-02-27 | 2017-03-14 | 2017-03-24 | Please Select... |  | D - Sponsor Delays | Sponsor
102535 | 16/LO/1977 | 220281 | HRA Approval | Adjustment with aphasia after stroke: Exploring the feasibility of a definitive phase III RCT for SUpporting wellbeing through PEeR Befriending (SUPERB) |  |  | No |  |  |  |  | 22 |  |  | Within 70 Days |  | 2017-02-13 | 2017-02-10 | 2017-02-13 | 2017-03-07 | Please Select... |  | D - Sponsor Delays | Sponsor