## Sheet1
ID | Trust ID | Submission ID | Meta Submission ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Added by User ID | Amended by User ID | Date Added | Date Amended | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Reasons for delay correspond to:
86044 | 926 | 4280 | 41 | 14/LO/1915 | 122548 | NHS Permission | Early education of skin cancer | 2015-10-06 | 2015-10-09 | No |  | 3 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86045 | 926 | 4280 | 41 | 14/LO/2195 | 165351 | NHS Permission | ARB (AR signaling in breast cancer) | 2015-10-28 | 2015-10-29 | Yes | 2016-04-18 | 1 | 172 | 173 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86046 | 926 | 4280 | 41 | 14/NE/0073 | 147215 | NHS Permission | BI836845 in women with Breast Cancer | 2015-11-18 | 2015-11-23 | Yes | 2016-04-19 | 5 | 148 | 153 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86047 | 926 | 4280 | 41 | 13/NS/0155 | 139913 | NHS Permission | Hysterectomy or Endometrial AbLaTion for Heavy menstrual bleeding HEALTH | 2015-08-27 | 2015-10-02 | Yes | 2015-10-14 | 36 | 12 | 48 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86048 | 926 | 4280 | 41 | 14/YH/1108 | 141368 | NHS Permission | SHAPE | 2015-11-18 | 2015-11-23 | Yes | 2016-03-24 | 5 | 122 | 127 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86049 | 926 | 4280 | 41 | 13/LO/1775 | 135580 | NHS Permission | PRAETORIAN | 2015-11-09 | 2015-11-10 | Yes | 2016-03-02 | 1 | 113 | 114 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86050 | 926 | 4280 | 41 | 14/LO/2103 | 162322 | NHS Permission | OSTRICH PKPD of intravenous salbutamol in paediatric acute severe asthma | 2015-10-12 | 2015-10-21 | Yes | 2015-11-26 | 9 | 36 | 45 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86051 | 926 | 4280 | 41 | 10/H0715/19 | 38478 | NHS Permission | Effects of the nervous system on cardiac conduction | 2015-10-14 | 2015-10-21 | Yes | 2015-10-26 | 7 | 5 | 12 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86052 | 926 | 4280 | 41 | 15/EE/0077 | 169447 | NHS Permission | AXAFA ? AFNET 5 | 2015-10-08 | 2015-10-08 | No |  | 0 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [9 empty] | Y | [5 empty] | NHS Provider
86053 | 926 | 4280 | 41 | 15/NW/0668 | 173723 | NHS Permission | FUTURE 5 | 2015-10-09 | 2015-10-14 | Yes | 2015-10-30 | 5 | 16 | 21 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86054 | 926 | 4280 | 41 | 15/LO/1055 | 173029 | NHS Permission | PARSIFAL 1 | 2015-10-29 | 2015-10-30 | Yes | 2015-11-16 | 1 | 17 | 18 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86055 | 926 | 4280 | 41 | 14/LO/1043 | 137864 | NHS Permission | LEAVO | 2015-06-25 | 2015-10-19 | Yes | 2015-12-28 | 116 | 70 | 186 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y |  | Y | [7 empty] | Sponsor
86056 | 926 | 4280 | 41 | 15/NE/0143 | 174391 | NHS Permission | BERGAMOT | 2015-10-19 | 2015-10-27 | No |  | 8 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86057 | 926 | 4280 | 41 | 15/SC/0003 | 154916 | NHS Permission | An Open-Label, Multicenter, Phase 1/2 Study of E7438 (EZH2 Histone Methyl Transferase [HMT] | 2015-10-15 | 2015-10-28 | Yes | 2015-12-10 | 13 | 43 | 56 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86058 | 926 | 4280 | 41 | 15/LO/1239 | 184169 | NHS Permission | AMBER | 2015-11-02 | 2015-11-03 | Yes | 2015-12-08 | 1 | 35 | 36 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86059 | 926 | 4280 | 41 | 15/NE/0167 | 171524 | NHS Permission | MLN9708?in?Multiple?Myeloma?Not?Treated?with?Stem?Cell?transplantation | 2015-10-14 | 2015-10-15 | No |  | 1 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86060 | 926 | 4280 | 41 | 14/YH/1259 | 163195 | NHS Permission | Comparison of ALitretinoin with PUVA (psoralen combined with ultraviolet A) as The First Line Treatm | 2015-10-09 | 2015-11-11 | Yes | 2016-01-08 | 33 | 58 | 91 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [5 empty] | Y | [8 empty] | NHS Provider
86061 | 926 | 4280 | 41 | 15/EM/0300 | 180135 | NHS Permission | A PHASE III, OPEN-LABEL, MULTICENTER, RANDOMIZED STUDY OF ATEZOLIZUMAB (ANTI-PD-L1 ANTIBODY) | 2015-09-01 | 2015-11-06 | Yes | 2015-12-16 | 66 | 40 | 106 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y |  | Y | [7 empty] | Sponsor
86062 | 926 | 4280 | 41 | 14/LO/2156 | 166004 | NHS Permission | A phase II study of VSN16R for Multiple Sclerosis related spasticity | 2015-10-15 | 2015-10-16 | Yes | 2015-10-30 | 1 | 14 | 15 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86063 | 926 | 4280 | 41 | 13/WM/0408 | 136755 | NHS Permission | RomiCar | 2015-11-05 | 2015-11-10 | No |  | 5 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86064 | 926 | 4280 | 41 | 15/LO/0788 | 166088 | NHS Permission | Pasireotide (SOM230) in patients with acromegaly | 2015-10-21 | 2015-11-10 | Yes | 2015-12-21 | 20 | 41 | 61 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86065 | 926 | 4280 | 41 | 14/WA/1075 | 150715 | NHS Permission | HeadPoST Version 2.1 | 2015-10-09 | 2015-10-21 | Yes | 2015-10-27 | 12 | 6 | 18 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86066 | 926 | 4280 | 41 | 15/LO/1175 | 180885 | NHS Permission | A Phase 3, Multicenter, Randomized, Double-blind, Placebo-controlled Trial of Oral RPC1063 as Induct | 2015-11-10 | 2015-11-16 | Yes | 2016-03-23 | 6 | 128 | 134 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86067 | 926 | 4280 | 41 | 15/NI/0188 | 185878 | NHS Permission | Longterm Study of Ferriprox? in Patients with Sickle Cell Disease | 2015-11-25 | 2015-11-30 | Yes | 2015-12-09 | 5 | 9 | 14 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86068 | 926 | 4280 | 41 | 15/EE/0161 | 177265 | NHS Permission | EASE-2 | 2015-11-25 | 2015-11-25 | Yes | 2016-01-06 | 0 | 42 | 42 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86069 | 926 | 4280 | 41 | 10/H0802/46 | 52863 | NHS Permission | REVIVED-BCIS2 | 2015-11-25 | 2015-11-27 | Yes | 2016-02-01 | 2 | 66 | 68 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86070 | 926 | 4280 | 41 | 15/NW/0696 | 184455 | NHS Permission | VITAL study | 2015-11-13 | 2015-11-18 | No |  | 5 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86071 | 926 | 4280 | 41 | 14/SC/1345 | 158326 | NHS Permission | PRISM | 2015-10-12 | 2015-10-15 | Yes | 2015-11-20 | 3 | 36 | 39 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86072 | 926 | 4280 | 41 | 15/WM/0207 | 178335 | NHS Permission | CANC - 4205 Carfilzomib in myeloma | 2015-11-30 | 2015-12-01 | Yes | 2016-01-06 | 1 | 36 | 37 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86073 | 926 | 4280 | 41 | 13/SC/0583 | 137948 | NHS Permission | Matchpoint | 2015-12-08 | 2015-12-16 | Yes | 2016-03-07 | 8 | 82 | 90 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86074 | 926 | 4280 | 41 | 15/LO/1595 | 183040 | NHS Permission | PRISM | 2015-11-19 | 2015-12-03 | Yes | 2015-12-15 | 14 | 12 | 26 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86075 | 926 | 4280 | 41 | 14/NE/0011 | 138347 | NHS Permission | STRIDER version 3.0 | 2015-09-30 | 2015-12-18 | Yes | 2016-01-22 | 79 | 35 | 114 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Sponsor
86076 | 926 | 4280 | 41 | 15/EE/0385 | 187687 | NHS Permission | NEPTUNE III | 2015-12-08 | 2015-12-09 | Yes | 2015-12-15 | 1 | 6 | 7 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86077 | 926 | 4280 | 41 | 15/NE/0270 | 180799 | NHS Permission | HAEM 4806 HESTIA2 | 2015-12-09 | 2015-12-09 | Yes | 2016-01-26 | 0 | 48 | 48 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86078 | 926 | 4280 | 41 | 15/LO/1612 | 186328 | NHS Permission | A phase III, randomised, open-label, controlled, multi-centre, global study of first-line MEDI4736 | 2015-12-10 | 2015-12-10 | Yes | 2016-03-02 | 0 | 83 | 83 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86079 | 926 | 4280 | 41 | 14/WA/1056 | 154468 | NHS Permission | AML19 | 2015-11-23 | 2015-12-14 | Yes | 2015-12-30 | 21 | 16 | 37 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86080 | 926 | 4280 | 41 | 15/EM/0487 | 184469 | NHS Permission | ENDURANCE-3 | 2015-12-14 | 2015-12-22 | Yes | 2016-01-21 | 8 | 30 | 38 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86081 | 926 | 4280 | 41 | 15/LO/1002 | 155611 | NHS Permission | Tendinopathy: Treatment effects and mechanisms 1 (Tendinopathy TEAM 1) | 2015-12-17 | 2015-12-18 | Yes | 2016-01-06 | 1 | 19 | 20 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86082 | 926 | 4280 | 41 | 15/LO/0500 | 149041 | NHS Permission | Facet Joint Injections | 2016-01-20 | 2016-01-20 | Yes | 2016-01-20 | 0 | 0 | 0 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86083 | 926 | 4280 | 41 | 15/SC/0548 | 174496 | NHS Permission | STAR_PAC | 2016-01-20 | 2016-01-20 | Yes | 2016-02-08 | 0 | 19 | 19 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86084 | 926 | 4280 | 41 | 15/SC/0406 | 182571 | NHS Permission | A PHASE 1B, OPEN-LABEL, DOSE-FINDING STUDY TO EVALUATE SAFETY, PHARMACOKINETICS AND PHARMACODYNAMICS | 2016-01-12 | 2016-01-13 | Yes | 2016-03-01 | 1 | 48 | 49 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86085 | 926 | 4280 | 41 | 15/YH/0484 | 188695 | NHS Permission | A Phase 3, Multicenter Study with a 36-Week Open-Label Period Followed by a Randomized | 2016-01-21 | 2016-02-01 | Yes | 2016-03-15 | 11 | 43 | 54 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86086 | 926 | 4280 | 41 | 15/SS/0186 | 190856 | NHS Permission | HEPA 5140 | 2016-01-11 | 2016-01-11 | Yes | 2016-01-21 | 0 | 10 | 10 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86087 | 926 | 4280 | 41 | 15/NW/0876 | 190510 | NHS Permission | Confirmatory validation of oral macimorelin as a growth hormone (GH) stimulation test (ST) | 2016-01-12 | 2016-01-15 | Yes | 2016-02-17 | 3 | 33 | 36 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86088 | 926 | 4280 | 41 | 14/NI/1113 | 155739 | NHS Permission | CONSISTENT CTO | 2016-01-18 | 2016-01-19 | Yes | 2016-02-04 | 1 | 16 | 17 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86089 | 926 | 4280 | 41 | 15/SC/0316 | 164933 | NHS Permission | E-FIT | 2016-01-11 | 2016-01-20 | Yes | 2016-03-18 | 9 | 58 | 67 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86090 | 926 | 4280 | 41 | 15/LO/1512 | 186421 | NHS Permission | GAST 4844-RPC3102 | 2016-01-11 | 2016-01-14 | Yes | 2016-03-21 | 3 | 67 | 70 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [9 empty] | Y | [5 empty] | Neither
86091 | 926 | 4280 | 41 | 15/LO/1684 | 184561 | NHS Permission | Dietary Interventions for FGS in IBD Version 1 | 2015-12-04 | 2016-01-13 | Yes | 2016-02-25 | 40 | 43 | 83 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y |  | Y | [9 empty] | Sponsor
86092 | 926 | 4280 | 41 | 15/NW/0627 | 181538 | NHS Permission | Phase 1B study of Axitinib plus Crizotinib in advanced solid tumours | 2015-12-09 | 2015-12-10 | Yes | 2016-03-18 | 1 | 99 | 100 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86093 | 926 | 4280 | 41 | 14/NW/1344 | 148295 | NHS Permission | The BEST study | 2016-01-07 | 2016-01-19 | Yes | 2016-03-22 | 12 | 63 | 75 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86094 | 926 | 4280 | 41 | 13/SC/0470 | 123518 | NHS Permission | Platelet-Oriented Inhibition in New TIA and minor ischemic stroke (POINT) | 2015-12-09 | 2016-01-27 | No |  | 49 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Both
86095 | 926 | 4280 | 41 | 14/EE/1293 | 164389 | NHS Permission | C-STICH | 2015-12-03 | 2016-01-12 | Yes | 2016-02-22 | 40 | 41 | 81 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | Y | [7 empty] | Sponsor
86096 | 926 | 4280 | 41 | 15/YH/0295 | 174242 | NHS Permission | STEADY Study | 2015-11-02 | 2015-11-10 | No |  | 8 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86097 | 926 | 4280 | 41 | 15/NW/0492 | 181246 | NHS Permission | Study of ACP-196 Versus Ibrutinib in previously treated CLL patients | 2016-01-12 | 2016-01-12 | No |  | 0 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86098 | 926 | 4280 | 41 | 14/SC/1333 | 146684 | NHS Permission | PATH-2 | 2015-12-15 | 2016-01-07 | Yes | 2016-03-11 | 23 | 64 | 87 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  |  | Y | [10 empty] | NHS Provider
86099 | 926 | 4280 | 41 | 13/SC/0309 | 128504 | NHS Permission | ELASTIC | 2015-12-02 | 2015-12-16 | No |  | 14 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86100 | 926 | 4280 | 41 | 13/LO/1207 | 86810 | NHS Permission | Stereotactic radiotherapy for wet AMD (STAR) | 2016-01-07 | 2016-01-28 | Yes | 2016-04-05 | 21 | 68 | 89 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86101 | 926 | 4280 | 41 | 14/SC/1416 | 156215 | NHS Permission | IgNiTE: Immunoglobulin in the treatment of encephalitis | 2016-01-21 | 2016-01-29 | No |  | 8 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86102 | 926 | 4280 | 41 | 14/LO/0369 | 143383 | NHS Permission | Ripple mapping identifies arrhythmogenic conduction channels | 2015-04-24 | 2016-02-04 | Yes | 2016-06-10 | 286 | 127 | 413 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y |  |  |  | Y | Y | [9 empty] | NHS Provider
86103 | 926 | 4280 | 41 | 15/LO/1575 | 180245 | NHS Permission | Gena99: Humancl rhFVIII treatment for HaemophiliaA patients | 2016-02-05 | 2016-02-12 | Yes | 2016-09-02 | 7 | 203 | 210 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86104 | 926 | 4280 | 41 | 15/EM/0179 | 177000 | NHS Permission | UNTOUCHED | 2016-03-08 | 2016-03-09 | Yes | 2016-06-16 | 1 | 99 | 100 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86105 | 926 | 4280 | 41 | 15/NW/0871 | 190741 | NHS Permission | HEPA 5014 | 2016-01-22 | 2016-01-29 | Yes | 2016-02-10 | 7 | 12 | 19 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86106 | 926 | 4280 | 41 | 15/YH/0485 | 186367 | NHS Permission | MUSC 5049: GP15-301 Study to compare GP2015 and Enbrel? in Rheumatoid Arthritis | 2016-01-28 | 2016-02-04 | Yes | 2016-04-07 | 7 | 63 | 70 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86107 | 926 | 4280 | 41 | 14/LO/2215 | 145834 | NHS Permission | The Efficacy and Safety of Chlorhexidine Gluconate Chip | 2016-02-29 | 2016-03-01 | No |  | 1 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86108 | 926 | 4280 | 41 | 15/LO/1829 | 187483 | NHS Permission | CLS001 | 2016-01-26 | 2016-02-01 | Yes | 2016-04-05 | 6 | 64 | 70 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86109 | 926 | 4280 | 41 | 15/LO/1812 | 190810 | NHS Permission | CANC - 5197 (Cassini/RIVA) | 2016-02-05 | 2016-02-05 | Yes | 2016-03-29 | 0 | 53 | 53 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86110 | 926 | 4280 | 41 | 15/LO/1635 | 178097 | NHS Permission | Abacus | 2016-02-18 | 2016-02-29 | Yes | 2016-05-26 | 11 | 87 | 98 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86111 | 926 | 4280 | 41 | 14/SS/1096 | 164274 | NHS Permission | RAPID-CTCA | 2016-01-22 | 2016-02-04 | Yes | 2016-05-11 | 13 | 97 | 110 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [9 empty] | Y | [5 empty] | NHS Provider
86112 | 926 | 4280 | 41 | 13/WA/0205 | 127379 | NHS Permission | AML 18 | 2016-01-25 | 2016-01-26 | Yes | 2016-01-28 | 1 | 2 | 3 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86113 | 926 | 4280 | 41 | 15/ES/0192 | 193776 | NHS Permission | Polaris 4 | 2016-02-12 | 2016-02-15 | Yes | 2016-03-14 | 3 | 28 | 31 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86114 | 926 | 4280 | 41 | 15/ES/0191 | 193753 | NHS Permission | Safety and Efficacy of Sofosbuvir/Velpatasvir/GS-9857 Fixed-Dose (GS-US-367-1173) | 2016-02-12 | 2016-02-15 | No |  | 3 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  | Y | [12 empty] | Sponsor
86115 | 926 | 4280 | 41 | 15/LO/0539 | 166304 | NHS Permission | RAIDER | 2016-02-19 | 2016-02-29 | No |  | 10 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86116 | 926 | 4280 | 41 | 14/NW/1294 | 158613 | NHS Permission | 4-stage LCI699 study with optional extension in Cushing's Disease | 2016-03-12 | 2016-03-13 | No |  | 1 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86117 | 926 | 4280 | 41 | 15/SW/0215 | 170092 | NHS Permission | Edwards CENTERA Transcatheter Heart Valve System | 2016-01-29 | 2016-02-08 | No |  | 10 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  | Y | [12 empty] | Sponsor
86118 | 926 | 4280 | 41 | 15/LO/0833 | 165266 | NHS Permission | IBIS 3 Feasibility version 1.0 | 2016-02-23 | 2016-02-24 | No |  | 1 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86119 | 926 | 4280 | 41 | 15/SC/0011 | 165787 | NHS Permission | META3876 | 2016-02-08 | 2016-02-08 | No |  | 0 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  | Y | [13 empty] | Sponsor
86120 | 926 | 4280 | 41 | 15/YH/0478 | 186697 | NHS Permission | The REGEREATE Study | 2016-01-29 | 2016-02-02 | Yes | 2016-04-04 | 4 | 62 | 66 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86121 | 926 | 4280 | 41 | 15/ES/0184 | 191039 | NHS Permission | Polaris 1 | 2016-02-01 | 2016-02-01 | Yes | 2016-03-07 | 0 | 35 | 35 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86122 | 926 | 4280 | 41 | 15/ES/0185 | 191042 | NHS Permission | Polaris 2 | 2016-02-01 | 2016-02-02 | Yes | 2016-03-14 | 1 | 41 | 42 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86123 | 926 | 4280 | 41 | 14/NE/1147 | 152258 | NHS Permission | HEALTH Trial. | 2016-01-22 | 2016-02-11 | Yes | 2016-02-15 | 20 | 4 | 24 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86124 | 926 | 4280 | 41 | 14/EE/1144 | 162403 | NHS Permission | Dipole Density Right (and left) Atrial Mapping and Assessment of Therapy In Complex Supraventricular | 2016-02-11 | 2016-02-17 | Yes | 2016-04-25 | 6 | 68 | 74 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86125 | 926 | 4280 | 41 | 15/EM/0546 | 194511 | NHS Permission | KESTREL | 2016-02-17 | 2016-02-23 | Yes | 2016-02-29 | 6 | 6 | 12 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86126 | 926 | 4280 | 41 | 15/LO/1600 | 182262 | NHS Permission | A phase II, openlabel, randomized study of GDC-0810 versus fulvestrant in postmenopausal women | 2016-02-19 | 2016-02-24 | Yes | 2016-04-18 | 5 | 54 | 59 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86127 | 926 | 4280 | 41 | 15/LO/2008 | 192214 | NHS Permission | MK1439A in treatment na?ve HIV1 infected subjects with NNRTI transmit | 2016-02-23 | 2016-02-25 | No |  | 2 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86128 | 926 | 4280 | 41 | 14/LO/2060 | 164866 | NHS Permission | Ripple AT | 2016-02-10 | 2016-02-29 | Yes | 2016-09-06 | 19 | 190 | 209 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [9 empty] | Y | [5 empty] | Neither
86129 | 926 | 4280 | 41 | 15/LO/1149 | 163191 | NHS Permission | RACE | 2016-02-29 | 2016-02-29 | No |  | 0 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86130 | 926 | 4280 | 41 | 15/EM/0470 | 183926 | NHS Permission | NEUR 4753 | 2016-01-22 | 2016-02-16 | Yes | 2016-06-20 | 25 | 125 | 150 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [6 empty] | Y | [8 empty] | Neither
86131 | 926 | 4280 | 41 | 15/LO/2121 | 193977 | NHS Permission | MK1439A STUDY (INFE 5425) | 2016-02-16 | 2016-03-04 | Yes | 2016-04-14 | 17 | 41 | 58 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86132 | 926 | 4280 | 41 | 15/YH/0535 | 190077 | NHS Permission | TRANSITION_LCZ696 pre/ post discharge in acute heart failure | 2016-03-03 | 2016-03-09 | Yes | 2016-08-25 | 6 | 169 | 175 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86133 | 926 | 4280 | 41 | 15/WM/0457 | 195511 | NHS Permission | An Open-Label Treatment Use Protocol for Daratumumab in Subjects with Multiple Myeloma Who Have Rece | 2016-02-22 | 2016-03-04 | Yes | 2016-03-30 | 11 | 26 | 37 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86134 | 926 | 4280 | 41 | 14/LO/2181 | 154300 | NHS Permission | RIO - Rucaparib Window of Opportunity Study | 2016-03-17 | 2016-03-21 | No |  | 4 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86135 | 926 | 4280 | 41 | 15/LO/1102 | 181603 | NHS Permission | MLN1117-1501, Phase 1b/2, NSCLC treatment with Docetaxel and MLN1117 | 2016-03-14 | 2016-03-14 | No |  | 0 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86136 | 926 | 4280 | 41 | 15/NW/0416 | 167060 | NHS Permission | MUK Eight | 2016-03-02 | 2016-03-22 | Yes | 2016-06-27 | 20 | 97 | 117 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86137 | 926 | 4280 | 41 | 15/WS/0274 | 191114 | NHS Permission | A Phase III, International, Randomized, Controlled Study of Rigosertib versus Physician's Choice of Treatment in Patients with Myelodysplastic Syndrome after Failure of a Hypomethylating Agent | 2016-03-23 | 2016-03-23 | No |  | 0 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86138 | 926 | 4280 | 41 | 13/EE/0335 | 137965 | NHS Permission | COOL-AMI EU case series clinical study | 2016-03-21 | 2016-03-23 | No |  | 2 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86139 | 926 | 4280 | 41 | 14/YH/0085 | 126738 | NHS Permission | FLAIR version 1.0 | 2016-03-14 | 2016-04-05 | No |  | 22 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86140 | 926 | 4280 | 41 | 14/WS/1113 | 153352 | NHS Permission | 3562 CAPE Study Version 1.0 | 2016-04-01 | 2016-06-17 | Yes | 2016-08-31 | 77 | 75 | 152 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86141 | 926 | 4280 | 41 | 15/LO/1549 | 169718 | NHS Permission | Pre-PRO | 2016-03-18 | 2016-04-19 | No |  | 32 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86142 | 926 | 4280 | 41 | 14/WM/1260 | 163072 | NHS Permission | PHAZAR | 2016-03-30 | 2016-04-14 | No |  | 15 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86143 | 926 | 4280 | 41 | 15/SC/0640 | 178883 | NHS Permission | Calypso | 2016-03-30 | 2016-05-04 | No |  | 35 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Neither
86144 | 926 | 4280 | 41 | 15/YH/0004 | 167453 | NHS Permission | ARIOS: Follow-up of infants born to mothers with in retosiban studies | 2016-03-30 | 2016-05-11 | No |  | 42 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Sponsor
86145 | 926 | 4280 | 41 | 15/YH/0003 | 167451 | NHS Permission | ZINN: Retosiban versus atosiban for spontaneous preterm | 2016-03-30 | 2016-05-09 | No |  | 40 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y |  | Y | [9 empty] | Sponsor
86146 | 926 | 4280 | 41 | 15/LO/0040 | 155632 | NHS Permission | Evaluate effect of GS6615 on Exercise capacity in subjects with HCM | 2016-03-27 | 2016-04-26 | No |  | 30 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [9 empty] | Y | [5 empty] | Neither
86147 | 926 | 4280 | 41 | 15/LO/1906 | 192701 | NHS Permission | A Randomised, Double-Blind, Placebo-Controlled Trial of the Safety | 2016-03-29 | 2016-04-22 | Yes | 2016-08-12 | 24 | 112 | 136 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [9 empty] | Y | [5 empty] | Neither
86148 | 926 | 4280 | 41 | 15/LO/2134 | 188448 | NHS Permission | Predictors 5.1 | 2016-02-24 | 2016-04-13 | Yes | 2016-04-22 | 49 | 9 | 58 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86149 | 926 | 4280 | 41 | 16/LO/0022 | 195696 | NHS Permission | Phase 3 study with GS-9883/F/TAF in HIV-1, treatment na?ve subjects | 2016-03-23 | 2016-04-05 | Yes | 2016-04-14 | 13 | 9 | 22 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Please Select...
86150 | 926 | 4280 | 41 | 15/LO/1908 | 184768 | NHS Permission | Phase I/IIa Study of DTP3 in Patients With Advanced Multiple Myeloma | 2016-03-15 | 2016-04-18 | No |  | 34 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86151 | 926 | 4280 | 41 | 16/LO/0022 | 195532 | NHS Permission | Phase 1 BAX 826 Dose-Escalation Safety Study, Protocol 291501 | 2016-03-23 | 2016-05-24 | No |  | 62 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Sponsor
86152 | 926 | 4280 | 41 | 16/LO/0304 | 199075 | NHS Permission | VELOCITY | 2016-03-28 | 2016-04-18 | Yes | 2016-04-19 | 21 | 1 | 22 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86153 | 926 | 4280 | 41 | 16/LO/0036 | 195359 | NHS Permission | GS-9883/F/TAF versus ABC/DTG/3TC in HIV-1, treatment-naive subjects | 2016-03-03 | 2016-04-01 | Yes | 2016-04-26 | 29 | 25 | 54 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86154 | 926 | 4280 | 41 | 15/LO/1879 | 186859 | NHS Permission | A Randomized, Open-Label Study of Ponatinib Versus Nilotinib in Patients with Chronic Myeloid Leukem | 2016-03-23 | 2016-04-01 | No |  | 9 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
86155 | 926 | 4280 | 41 | 16/EM/0133 | 184873 | NHS Permission | CAIN457H2315 | 2016-04-08 | 2016-06-08 | Yes | 2016-06-20 | 61 | 12 | 73 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86156 | 926 | 4280 | 41 | 15/WM/0268 | 180518 | NHS Permission | ENRICH | 2016-03-07 | 2016-04-05 | No |  | 29 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86157 | 926 | 4280 | 41 | 15/LO/2124 | 192795 | NHS Permission | The ?METRIC? Study | 2016-03-23 | 2016-04-08 | Yes | 2016-05-13 | 16 | 35 | 51 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86158 | 926 | 4280 | 41 | 15/YH/0530 | 886569 | NHS Permission | CLARITY | 2016-03-15 | 2016-04-12 | No |  | 28 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86159 | 926 | 4280 | 41 | 16/NW/0071 | 195362 | NHS Permission | Pelle-926-201- Double- Blind, Randomized, Vehicle-Controlled Proof of Concept Clinical Trial | 2016-03-29 | 2016-04-18 | Yes | 2016-06-07 | 20 | 50 | 70 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86160 | 926 | 4280 | 41 | 16/LO/0026 | 195795 | NHS Permission | Phase 3 open-label switch study with GS-9883/F/TAF in HIV-1 subjects | 2016-03-23 | 2016-04-20 | Yes | 2016-05-17 | 28 | 27 | 55 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86161 | 926 | 4280 | 41 | 16/ES/0001 | 193859 | NHS Permission | GED 0301 CD 002 PhIII study for subjects with Active Crohns Disease | 2016-03-31 | 2016-04-20 | No |  | 20 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86162 | 926 | 4280 | 41 | 16/LO/0152 | 193306 | NHS Permission | Evaluate the Effect of a Digital Disease Management Tool in DM Patient | 2016-03-22 | 2016-04-21 | Yes | 2016-05-27 | 30 | 36 | 66 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86163 | 926 | 4280 | 41 | 15/LO/1876 | 184353 | NHS Permission | A Phase 2, Randomized, Double-Blind, Placebo-Controlled, Parallel Group, Multi-Center Study | 2016-03-28 | 2016-04-26 | No |  | 29 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86164 | 926 | 4280 | 41 | 16/WS/0077 | 202213 | NHS Permission | (duplicate) M10-870 Adalimumab in Paediatric Ulcerative Colitis (Ext) | 2016-05-03 | 2016-05-03 | Yes | 2016-06-01 | 0 | 29 | 29 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86165 | 926 | 4280 | 41 | 15/LO/1945 | 184624 | NHS Permission | Prophylaxis against acute attacks of Hereditary Angioedema (HAE) | 2016-03-26 | 2016-05-04 | Yes | 2016-05-25 | 39 | 21 | 60 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86166 | 926 | 4280 | 41 | 15/LO/2034 | 190228 | NHS Permission | A Phase 1b Study to Evaluate safety and clinical activity of Pembrolizumab (MK3475) in combination | 2016-03-29 | 2016-05-04 | No |  | 36 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86167 | 926 | 4280 | 41 | 16/LO/0092 | 194133 | NHS Permission | A PHASE Ib/II STUDY EVALUATING THE SAFETY AND EFFICACY OF OBINUTUZUMAB IN COMBINATION WITH POLATUZUM | 2016-03-23 | 2016-05-09 | No |  | 47 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86168 | 926 | 4280 | 41 | 15/LO/1077 | 173350 | NHS Permission | ABC-07 | 2016-03-17 | 2016-05-09 | No |  | 53 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86169 | 926 | 4280 | 41 | 11/SS/0100 | 84669 | NHS Permission | Fluoxetine Or Control Under Supervision (FOCUS) | 2016-02-29 | 2016-05-09 | No |  | 70 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86170 | 926 | 4280 | 41 | 15/EE/0464 | 183877 | NHS Permission | LJPC-501 in Patients with Catecholamine-Resistant Hypotension | 2016-03-23 | 2016-05-16 | No |  | 54 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y |  | Y | [9 empty] | Sponsor
86171 | 926 | 4280 | 41 | 14/YH/1199 | 153953 | NHS Permission | GALACTIC | 2016-03-10 | 2016-05-23 | No |  | 74 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86172 | 926 | 4280 | 41 | 15/SS/0194 | 173717 | NHS Permission | A multicentre 52 week double blind Asthma study with QMF149 | 2016-04-11 | 2016-05-19 | No |  | 38 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Neither
86173 | 926 | 4280 | 41 | 13/LO/1616 | 137039 | NHS Permission | NCRN - 2888 MEDI4736 in Advanced Solid Tumors | 2016-03-22 | 2016-05-19 | Yes | 2016-05-24 | 58 | 5 | 63 | Yes | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
86174 | 926 | 4280 | 41 | 12/LO/0864 | 87348 | NHS Permission | FIESTA | 2016-03-16 | 2016-05-20 | No |  | 65 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86175 | 926 | 4280 | 41 | 14/SC/0171 | 120104 | NHS Permission | Add-Aspirin | 2016-03-11 | 2016-06-08 | No |  | 89 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Sponsor
86176 | 926 | 4280 | 41 | 15/WA/0118 | 156108 | NHS Permission | The ALMASED Concept against Overweight and Obesity and Related Health Risk (ACOORH) | 2016-03-22 | 2016-05-24 | No |  | 63 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86177 | 926 | 4280 | 41 | 15/EM/0422 | 187040 | NHS Permission | BAX69 | 2016-03-23 | 2016-05-25 | No |  | 63 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86178 | 926 | 4280 | 41 | 13/ES/0123 | 119188 | NHS Permission | NiCCC Trial (BIBF1120) | 2016-03-21 | 2016-06-01 | No |  | 72 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86179 | 926 | 4280 | 41 | 16/WA/0060 | 195792 | NHS Permission | Idasanutlin in relapsed/refractory AML | 2016-03-15 | 2016-06-13 | Yes | 2016-08-30 | 90 | 78 | 168 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86180 | 926 | 4280 | 41 | 15/NE/0144 | 179243 | NHS Permission | GAST 4684 - RPC3101 | 2016-03-21 | 2016-03-23 | No |  | 2 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
86181 | 926 | 4280 | 41 | 14/NW/1488 | 164229 | NHS Permission | AD4833/TOMM40_303 Extension Alzheimer's Disease study | 2016-03-22 | 2016-06-29 | No |  | 99 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Sponsor
91629 | 926 | 4280 | 41 | 14/NW/1219 | 160371 | NHS Permission | NERVES | 2016-03-31 | 2016-08-05 | No |  | 127 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Neither
91630 | 926 | 4280 | 41 | 16/LO/1379 | 183308 | HRA Approval | STAR MAPPING |  |  | No | [7 empty] | 2016-08-16 | 2016-09-23 |  |  | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
91631 | 926 | 4280 | 41 | 15/NW/0592 | 185435 | NHS Permission | DIAB 3796 | 2015-12-04 | 2016-07-01 | No |  | 210 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y |  | Y | [7 empty] | Sponsor
91632 | 926 | 4280 | 41 | 16/LO/0677 | 190078 | HRA Approval | A multicenter, randomized, 52-week, double-blind, parallelgroup, active controlled study to compare |  |  | Yes | 2016-09-22 | [6 empty] | 2016-04-21 | 2016-06-16 | 2016-06-12 | 2016-07-29 | Please Select... | 2016-08-18 | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
91633 | 926 | 4280 | 41 | 16/WM/0197 | 202991 | HRA Approval | RO5459072 in Primary Sjogren's Syndrome |  |  | No | [7 empty] | 2016-04-28 | 2016-07-07 | 2016-07-19 | 2016-08-11 | Please Select... | 2016-09-19 | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Sponsor
91634 | 926 | 4280 | 41 | 16/LO/0582 | 191697 | HRA Approval | C31005 MLN0128 and MLN0128+MLN117 Compared With Everolimus in mccRCC |  |  | No | [7 empty] | 2016-05-17 | 2016-06-23 | 2016-07-26 | 2017-07-28 | Please Select... | 2016-09-28 | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
91635 | 926 | 4280 | 41 | 16/LO/0919 | 201803 | HRA Approval | MEDI4736 with Tremelimumab in advanced solid tumours |  |  | No | [7 empty] | 2016-05-16 | 2016-07-13 | 2016-08-30 | 2016-09-09 | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Neither
91636 | 926 | 4280 | 41 | 14/WA/1118 | 159836 | NHS Permission | Postoperative adjuvant treatment for HPV positive tumours (PATHOS) | 2016-03-21 | 2016-07-05 | No |  | 106 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Both
91637 | 926 | 4280 | 41 | 16/LO/0877 | 202257 | HRA Approval | A PHASE 3, MULTICENTER, MULTINATIONAL, RANDOMIZED, OPEN-LABEL, PARALLEL-ARM STUDY OF AVELUMAB*(MSB00 |  |  | No | [7 empty] | 2016-08-24 | 2016-09-05 | 2016-09-06 | 2016-09-09 | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
91638 | 926 | 4280 | 41 | 16/EM/0193 | 190690 | HRA Approval | The dal-GenE trial |  |  | No | [7 empty] | 2016-06-14 | 2016-06-14 | 2016-09-01 | 2016-09-09 | Please Select... | 2016-09-27 | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Neither
91639 | 926 | 4280 | 41 | 16/NE/0147 | 204478 | HRA Approval | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Phase III Study to Evaluate the Efficacy |  |  | No | [7 empty] | 2016-06-03 | 2016-06-15 | 2016-08-18 | 2016-08-22 | Please Select... | 2016-09-05 | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [7 empty] | Y | [7 empty] | Sponsor
91640 | 926 | 4280 | 41 | 16/NE/0121 | 196233 | HRA Approval | SEM200-008 Study |  |  | Yes | 2016-09-14 | [6 empty] | 2016-06-14 | 2016-06-08 | 2016-07-29 | 2016-08-22 | Please Select... | 2016-08-25 | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
91641 | 926 | 4280 | 41 | 15/EM/0440 | 178108 | NHS Permission | AZTEC | 2016-03-15 | 2016-07-21 | No |  | 128 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 |  |  |  | Y | [11 empty] | Sponsor
91642 | 926 | 4280 | 41 | 16/LO/1060 | 202362 | HRA Approval | EXPEDITION-2 |  |  | Yes | 2016-08-08 | [6 empty] | 2016-07-05 | 2016-07-12 | 2016-07-25 | 2016-07-29 | Please Select... | 2016-08-01 | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
91643 | 926 | 4280 | 41 | 16/NW/0253 | 188110 | HRA Approval | M13-542 Phase 3 ABT-494 |  |  | Yes | 2016-09-20 | [6 empty] | 2016-05-18 | 2016-08-10 | 2016-07-18 | 2016-08-30 | Please Select... | 2016-09-06 | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Neither
91644 | 926 | 4280 | 41 | 15/LO/1760 | 184374 | NHS Permission | BISCAY | 2016-03-23 | 2016-07-19 | Yes | 2016-08-04 | 118 | 16 | 134 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Neither
91645 | 926 | 4280 | 41 | 16/SC/0068 | 196245 | NHS Permission | MEDI4736 | 2016-03-29 | 2016-07-20 | Yes | 2016-08-31 | 113 | 42 | 155 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Neither
91646 | 926 | 4280 | 41 | 15/SS/0107 | 173327 | NHS Permission | SPARE | 2016-03-30 | 2016-07-25 | No |  | 117 |  |  | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Both
91647 | 926 | 4280 | 41 | 16/NS/0070 | 208445 | HRA Approval | The HeartFlow ADVANCE Registry |  |  | No | [7 empty] | 2016-07-28 | 2016-07-22 | 2016-05-09 | 2016-09-16 | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [15 empty] | Please Select...
91648 | 926 | 4280 | 41 | 16/NW/0506 | 207353 | HRA Approval | Achilles |  |  | No | [7 empty] | 2016-07-12 | 2016-08-24 | 2016-08-22 | 2016-09-08 | Please Select... | 2016-09-08 | Unknown | Unknown | 2016-10-28 | 2016-10-31 | [5 empty] | Y | [9 empty] | Neither
91649 | 926 | 4280 | 41 | 16/LO/0498 | 196286 | NHS Permission | NAVIGATE | 2016-04-04 | 2016-08-23 | Yes | 2016-09-14 | 141 | 22 | 163 | No | [6 empty] | Please Select... |  | Unknown | Unknown | 2016-10-28 | 2016-10-31 | Y | [14 empty] | Sponsor