## Sheet1
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for delay correspond to:
130200 | 17/LO/0925 | 223376 | M15-554- Comparing ABT-494 to Placebo in PsA subjects | Yes | 2018-05-18 | 18 | 109 | 127 | 2017-08-18 | 2018-01-11 | 2018-01-08 | 2018-01-23 | 2018-01-29 | 2018-02-15 |  | Y |  |  |  | Y |  |  |  |  | Sponsor
130201 | 17/LO/0926 | 222889 | Phase 3 PsA study subjects with inadeqate response to | Yes | 2018-02-19 | 18 | 21 | 39 | 2017-09-07 | 2018-01-11 | 2018-01-08 | 2018-01-29 | 2018-01-29 | 2018-02-15 | [10 empty] | Please Select...
130202 | 17/YH/0228 | 222492 | CALM II | Yes | 2018-08-21 | 26 | 146 | 172 | 2017-09-15 | 2018-03-02 | 2017-10-05 | 2018-03-28 | 2018-03-28 | 2018-03-29 |  | Y |  | Y |  | Y |  |  |  |  | Sponsor
130203 | 17/NW/0662 | 220156 | APPRAISE ATP | Yes | 2018-07-16 | 61 | 55 | 116 | 2017-12-01 | 2018-03-22 | 2018-03-22 | 2018-05-14 | 2018-05-22 | 2018-06-06 | Y |  |  | Y |  |  |  | Y |  |  | Sponsor
130204 | 17/NE/0377 | 233847 | A Phase 3b Study to Reduce the Incidence of Pre-dialysis Hyperkalaemia | Yes | 2018-05-21 | 32 | 31 | 63 | 2017-12-20 | 2018-03-19 | 2018-02-19 | 2018-04-12 | 2018-04-20 | 2018-04-24 | [10 empty] | Please Select...
130205 | 18/NW/0075 | 229477 | Study of the safety & effectiveness of JNJ-56136379 in hepatitis B | Yes | 2018-06-07 | 92 | 13 | 105 | 2018-01-26 | 2018-02-22 | 2018-03-06 | 2018-05-16 | 2018-05-25 | 2018-06-01 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
130206 | 17/SC/0650 | 235509 | SHP647 as induction therapy in moderate to severe Ulcerative Colitis | Yes | 2018-09-11 | 147 | 40 | 187 | 2018-01-10 | 2018-03-08 | 2018-03-07 | 2018-07-17 | 2018-08-02 | 2018-08-06 | [5 empty] | Y |  | Y |  |  | Sponsor
130207 | 17/LO/0948 | 222446 | FABULAS | Yes | 2018-02-21 | 31 | 20 | 51 | 2017-05-25 | 2018-01-01 | 2017-11-01 | 2018-02-01 | 2018-02-01 | 2018-02-12 | [10 empty] | Please Select...
130208 | 17/LO/0334 | 214459 | FLO-ELA | Yes | 2018-03-31 | 35 | 52 | 87 | 2018-01-03 | 2018-01-03 | 2017-03-29 | 2018-01-25 | 2018-02-07 | 2018-03-14 |  |  |  | Y | [6 empty] | Sponsor
130209 | 17/SC/0216 | 223931 | ACE-LY-110 | Yes | 2018-03-21 | 16 | 56 | 72 | 2017-05-16 | 2018-01-08 | 2017-06-30 | 2017-09-11 | 2018-01-24 | 2018-03-19 | [10 empty] | Please Select...
130210 | 17/WM/0299 | 209719 | T2NOW | Yes | 2018-03-16 | 45 | 21 | 66 | 2017-09-15 | 2018-01-09 | 2017-11-20 | 2018-02-26 | 2018-02-23 | 2018-03-06 | [10 empty] | Please Select...
130211 | 17/NW/0511 | 226627 | ITI rFVIIIFc study in HaemophiliaA Pts who failed previous ITI therapy | No |  | 115 |  |  | 2018-01-09 | 2018-01-09 | 2017-11-06 | 2018-03-05 | 2018-05-04 | 2018-05-04 | [6 empty] | Y | Y |  |  | Both
130212 | 17/LO/1725 | 179050 | Pacemaker therapy for drug-refractory symptoms in mid-cavity HCM | Yes | 2018-02-13 | 8 | 35 | 43 | 2018-01-01 | 2018-01-01 | 2017-12-20 | 2018-01-09 | 2018-01-09 | 2018-02-08 | [10 empty] | Please Select...
130213 | 17/NE/0061 | 215780 | CONVINCE - Protocol Version 2.1 29th November 2016 | No |  | 196 |  |  | 2017-12-22 | 2018-01-18 | 2017-07-25 | 2018-04-30 | 2018-08-02 | 2018-08-08 |  |  |  |  | Y | Y |  | Y |  |  | Both
130214 | 16/LO/1244 | 200385 | CANC 5642 | No |  | 141 |  |  | 2016-07-21 | 2018-02-01 | 2016-10-20 | 2017-02-22 | 2018-06-22 | 2018-10-04 |  |  |  | Y | Y | [5 empty] | Both
130215 | 18/LO/0045 | 233362 | Study to test safety/efficacy of CIT treatment in NSCLC patients | Yes | 2018-08-07 | 160 | 28 | 188 | 2018-01-30 | 2018-01-31 | 2018-02-07 | 2018-06-26 | 2018-07-10 | 2018-07-27 |  | Y | [8 empty] | Sponsor
130216 | 17/EE/0040 | 222216 | ENCIRCLE Emergency Cerclage in Twins at Imminent Risk of preterm birth | No |  | 28 |  |  | 2018-02-08 | 2018-02-08 | 2017-03-02 | 2018-03-08 | 2018-03-08 | 2018-04-09 | [5 empty] | Y |  |  |  |  | Neither
130217 | 16/NW/0629 | 211995 | CF START | No |  | 102 |  |  | 2018-02-09 | 2018-02-09 | 2016-09-22 | 2018-05-10 | 2018-05-22 | 2018-06-19 |  |  |  |  | Y | Y | Y |  |  |  | NHS Provider
130218 | 17/SC/0526 | 227616 | CA209-9ER: Advanced or Metastatic Renal Cell Carcinoma | Yes | 2018-07-24 | 155 | 4 | 159 | 2018-02-15 | 2018-02-15 | 2017-11-20 | 2018-07-18 | 2018-07-20 | 2018-07-23 | [7 empty] | Y |  |  | Sponsor
130220 | 17/SC/0638 | 236603 | BCX7353 long term safety study | Yes | 2018-04-25 | 37 | 28 | 65 | 2018-01-10 | 2018-02-19 | 2018-01-25 | 2018-03-20 | 2018-03-28 | 2018-03-30 | [10 empty] | Please Select...
130221 | 17/LO/2064 | 232321 | Phase 2 study of BGB-3111 and Obinutuzumab in Follicular Lymphoma | Yes | 2018-12-10 | 122 | 0 | 122 | 2018-01-17 | 2018-08-10 | 2018-06-12 | 2018-11-30 | 2018-12-10 | 2018-12-10 |  |  |  | Y | Y | [5 empty] | Both
130222 | 17/EE/0382 | 220851 | PROFILE - personalised medicine in Crohn's disease | Yes | 2018-05-24 | 9 | 84 | 93 | 2018-01-08 | 2018-02-20 | 2017-11-02 | 2018-02-21 | 2018-03-01 | 2018-03-20 |  |  |  |  | Y | [5 empty] | NHS Provider
130223 | 17/EE/0480 | 235288 | Phase 3 Study of Pembro with/without Epacadostat in 1L Urothelial Carc | No |  |  |  |  | 2017-11-28 | 2018-02-21 | 2018-02-05 | [5 empty] | Y | [7 empty] | Sponsor
130224 | 18/NE/0008 | 223912 | PRESTO (Treatment of stable thoracolumbar fractures: feasibility) | Yes | 2018-06-08 | 55 | 52 | 107 | 2017-11-03 | 2018-02-21 | 2018-03-20 | 2018-04-13 | 2018-04-17 | 2018-04-18 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
130225 | 17/SC/0023 | 220276 | The HarbOR study | Yes | 2018-12-11 | 97 | 187 | 284 | 2018-03-02 | 2018-03-02 | 2017-02-08 | 2018-05-30 | 2018-06-07 | 2018-06-12 | [5 empty] | Y |  | Y |  |  | Sponsor
130226 | 17/YH/0436 | 234886 | BP40234: RO6874281 in combination with atezolizumab in solid tumours | Yes | 2018-06-26 | 32 | 28 | 60 | 2018-02-15 | 2018-04-27 | 2018-02-27 | 2018-05-17 | 2018-05-29 | 2018-06-05 | [10 empty] | Please Select...
130227 | 17/SW/0010 | 197027 | Novel use of TXA to reduce the need for nasal packing in epistaxis | No |  | 46 |  |  | 2018-03-08 | 2018-03-08 | 2017-03-14 | 2018-04-13 | 2018-04-23 | 2018-05-30 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
130228 | 17/LO/1715 | 226230 | PHERGain | Yes | 2018-10-22 | 159 | 69 | 228 | 2018-03-08 | 2018-03-08 | 2018-06-05 | 2018-08-13 | 2018-08-14 | 2018-08-21 | [5 empty] | Y |  | Y |  |  | Both
130229 | 17/NW/0193 | 216411 | IntAct- IFA to prevent anastomotic leak in rectal cancer surgery | No |  | 35 |  |  | 2017-11-09 | 2018-03-09 | 2017-04-20 | 2018-04-13 | 2018-04-13 | 2018-04-13 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
130230 | 18/YH/0014 | 224065 | The ACTIVE TRIAL | Yes | 2019-01-11 | 115 | 182 | 297 | 2018-03-13 | 2018-03-20 | 2018-02-13 | 2018-07-11 | 2018-07-13 | 2018-07-23 | [5 empty] | Y | Y | Y |  |  | Sponsor
130231 | 17/WS/0137 | 228128 | VNS-REHAB | No |  | 69 |  |  | 2018-03-08 | 2018-03-14 | 2017-09-27 | 2018-05-10 | 2018-05-22 | 2018-05-24 | [5 empty] | Y |  |  |  |  | Neither
130232 | 18/LO/0227 | 228539 | A feasibility study of ACT for people with MND (Phase 1) v1 | Yes | 2018-11-12 | 42 | 53 | 95 | 2018-02-22 | 2018-08-09 | 2018-03-13 | 2018-09-07 | 2018-09-20 | 2018-09-27 | [7 empty] | Y |  |  | Sponsor
130233 | 17/NE/0124 | 216591 | TEMPO Study | Yes | 2018-08-08 | 32 | 113 | 145 | 2017-04-12 | 2018-03-16 | 2017-07-10 | 2018-03-09 | 2018-04-17 | 2018-05-25 | [5 empty] | Y |  |  |  |  | Neither
130234 | 17/LO/1847 | 216867 | MUK Twelve | No |  |  |  |  | 2017-12-04 | 2018-03-16 | 2018-01-04 | [10 empty] | Y |  |  | Both
130235 | 17/EM/0361 | 234065 | 215MS202 Efficacy & Safety of BIIB033 as an Add-on Therapy in RMS | No |  | 157 |  |  | 2017-10-04 | 2018-01-12 | 2018-01-11 | 2018-03-28 | 2018-06-18 |  |  |  | Y | [7 empty] | Sponsor
130236 | 17/LO/1289 | 226881 | A Phase 2b Ublituximab, TGR-1202, Bendamustine in NHL patients | Yes | 2018-05-23 | 116 | 9 | 125 | 2017-10-27 | 2018-01-18 | 2017-10-17 | 2018-05-11 | 2018-05-14 | 2018-05-22 |  |  |  |  | Y |  |  | Y |  |  | NHS Provider
130237 | 17/SS/0052 | 196827 | Early valve surgery for severe asymptomatic aortic stenosis (EVoLVeD) | Yes | 2018-10-10 | 34 | 174 | 208 | 2018-01-31 | 2018-03-16 | 2017-06-17 | 2018-04-05 | 2018-04-19 | 2018-04-27 | [5 empty] | Y |  |  |  |  | Sponsor
130238 | 18/LO/0079 | 232937 | LJPC-401 for iron overload in adults with TDT | Yes | 2018-06-12 | 39 | 29 | 68 | 2018-02-09 | 2018-04-05 | 2018-04-05 | 2018-04-26 | 2018-05-14 | 2018-05-15 | [10 empty] | Please Select...
130239 | 17/LO/1624 | 195099 | Effect of dietary nitrate ingestion in Heart Failure (DiNOmo-HF) | No |  | 45 |  |  | 2017-09-21 | 2018-04-10 | 2018-03-22 | 2018-05-21 | 2018-05-25 | 2018-05-25 | [5 empty] | Y |  |  |  |  | Neither
130240 | 18/LO/0099 | 240520 | Fitusiran in Patients With Hemophilia A or B Without Inhibitory Ab | No |  |  |  |  | 2017-08-01 | 2018-08-08 | 2018-03-22 | [6 empty] | Y | Y | [5 empty] | Both
130241 | 17/SC/0039 | 220282 | MAGPIE | Yes | 2018-09-18 | 85 | 74 | 159 | 2018-04-05 | 2018-04-12 | 2017-04-18 | 2018-06-18 | 2018-07-06 | 2018-09-03 |  |  |  |  | Y |  |  | Y |  |  | Both
130242 | 17/EM/0281 | 229054 | 204862 Phase 3 switch study -TAF regimen to DTG + 3TC in HIV-1 adults | No |  | 17 |  |  | 2018-02-15 | 2018-04-13 | 2018-02-15 | 2018-04-26 | 2018-04-30 | 2018-05-08 |  |  | Y | [7 empty] | Sponsor
130243 | 18/LO/0235 | 240315 | An Open Label Extension Study of GBT440 Administered Orally to Patients with Sickle Cell Disease Who Have Participated in GBT440 Clinical Trials | No |  |  |  |  | 2018-02-09 | 2018-04-17 | 2018-04-17 | [6 empty] | Y |  |  |  | Y |  |  | Sponsor
130244 | 17/LO/0825 | 223457 | Filgotinib, GS-9876, GS-4059 in Adults with Active Sjogren?s Syndrome | No |  |  |  |  | 2018-03-26 | 2018-04-18 | 2017-06-30 | [10 empty] | Y |  |  | Sponsor
130245 | 17/SC/0639 | 236312 | BMN 270-302 Gene therapy study in severe Haemophilia A patients | No |  | 5 |  |  | 2018-01-08 | 2018-04-19 | 2018-02-26 | 2018-04-05 | 2018-04-24 | 2018-04-11 | [5 empty] | Y |  |  |  |  | Neither
130246 | 17/YH/0289 | 231276 | A phase 1/2 study with Acalabrutinib and AZD6738 in high risk CLL | No |  |  |  |  | 2018-01-11 | 2018-04-23 | 2017-10-18 | [6 empty] | Y | [6 empty] | Sponsor
130247 | 18/EE/0079 | 237389 | APEX 2 BCX7353 in Prevention of HAE Attacks | Yes | 2018-07-10 | 23 | 55 | 78 | 2018-02-16 | 2018-04-23 | 2018-04-18 | 2018-04-11 | 2018-05-16 | 2018-05-21 | [10 empty] | Please Select...
130248 | 17/SC/0090 | 215068 | c-TRAK TN | No |  | 69 |  |  | 2017-11-08 | 2018-08-17 | 2017-07-05 | 2018-10-16 | 2018-10-25 | 2018-10-26 |  |  |  | Y | Y | [5 empty] | Both
130249 | 17/YH/0369 | 232340 | BGB-3111-304 | No |  | 25 |  |  | 2017-11-20 | 2018-08-30 | 2018-01-03 | 2018-08-16 | 2018-09-24 | 2018-09-28 |  |  |  |  | Y | Y |  | Y |  |  | Both
130250 | 17/SC/0609 | 235575 | Daiichi Sankyo DS8201-A-U201 (DS-8201a) | Yes | 2018-07-02 | 18 | 49 | 67 | 2017-12-22 | 2018-04-26 | 2018-01-08 | 2018-04-04 | 2018-05-14 | 2018-06-27 | [10 empty] | Please Select...
130251 | 18/LO/0364 | 237978 | Nalu Medical NAL-02-2016-FS SCS Feasibillity trial | Yes | 2018-06-13 | 48 | 0 | 48 | 2018-03-06 | 2018-04-26 | 2018-04-23 | 2018-06-05 | 2018-06-13 | 2018-06-13 | [10 empty] | Please Select...
130252 | 16/LO/2150 | 201093 | OCTOVA | No |  | 187 |  |  | 2018-04-20 | 2018-05-02 | 2017-01-26 | 2018-10-15 | 2018-11-05 | 2018-11-23 | [7 empty] | Y |  |  | Sponsor
130253 | 18/LO/0149 | 236716 | MO39193 - Atezolizumab + Chemotherapy in early relapsing TNBC | Yes | 2018-08-16 | 95 | 10 | 105 | 2018-02-07 | 2018-05-03 | 2018-04-17 | 2018-06-13 | 2018-08-06 | 2018-08-15 |  |  |  |  | Y |  |  | Y |  |  | Both
130254 | 18/SC/0095 | 235876 | BREEZE-AD4 - Baricitinib in moderate to severe atopic dermatitis | No |  | 40 |  |  | 2018-02-15 | 2018-05-09 | 2018-04-05 | 2018-06-18 | 2018-06-18 |  |  |  |  | Y | Y | [5 empty] | Both
130255 | 18/LO/0333 | 216039 | A prospective study into the utility of qHBsAg in management of CHB v1 | Yes | 2018-07-04 | 43 | 12 | 55 | 2018-05-10 | 2018-05-10 | 2018-04-17 | 2018-06-22 | 2018-06-22 | 2018-06-22 | [10 empty] | Please Select...
130256 | 18/LO/0052 | 228730 | A study to evaluate JNJ-64300535 DNA vaccine in chronic Hepatitis B | No |  |  |  |  | 2018-01-11 | 2018-05-11 | 2018-03-22 | [6 empty] | Y |  |  |  | Y |  |  | Sponsor
130257 | 16/NS/0106 | 212541 | RAACENO | Yes | 2018-10-18 | 37 | 118 | 155 | 2017-11-15 | 2018-05-16 | 2017-04-04 | 2018-06-01 | 2018-06-22 | [6 empty] | Y |  |  |  |  | Neither
130258 | 18/WA/0138 | 242665 | D5136C00009 - Hestia 3, Phase 3 study of Ticagrelor in Paediatric SCD | Yes | 2018-11-13 | 48 | 57 | 105 | 2018-05-18 | 2018-07-31 | 2018-07-18 | 2018-08-23 | 2018-09-17 | 2018-09-18 | [7 empty] | Y |  |  | NHS Provider
130259 | 18/LO/0779 | 235161 | B1371019 | No |  |  |  |  | 2018-04-23 | 2018-08-10 | [7 empty] | Y |  |  |  | Y |  |  | Sponsor
130260 | 17/YH/0386 | 233803 | Cryo AF Global Registry | Yes | 2018-07-27 | 17 | 49 | 66 | 2017-11-07 | 2018-05-22 | 2018-01-11 | 2018-06-08 | 2018-06-08 | 2018-07-04 | [10 empty] | Please Select...
130261 | 16/WM/0472 | 211270 | CONFIRM | Yes | 2018-10-10 | 87 | 47 | 134 | 2017-05-05 | 2018-05-29 | 2017-03-14 | 2018-05-09 | 2018-08-24 | 2018-09-19 |  |  |  |  | Y |  |  | Y |  |  | Both
130262 | 17/YH/0262 | 219133 | TRITON Trial v1.0 | Yes | 2018-09-18 | 5 | 104 | 109 | 2017-10-09 | 2018-06-01 | 2017-11-07 | 2017-11-21 | 2018-06-06 | 2018-07-21 | [5 empty] | Y |  |  |  |  | Neither
130263 | 18/WS/0073 | 242354 | NEFECON IN PATIENTS WITH PRIMARY IGA-Nephropathy Caliditas | Yes | 2018-10-31 | 100 | 49 | 149 | 2018-03-02 | 2018-06-04 | 2018-06-04 | 2018-09-04 | 2018-09-12 | 2018-09-20 |  |  |  | Y | [6 empty] | Sponsor
130264 | 18/NE/0125 | 238346 | PROFHER2 Trial - Version 1.0 | Yes | 2018-10-03 | 62 | 58 | 120 | 2018-05-01 | 2018-06-05 | 2018-05-15 | 2018-07-05 | 2018-08-06 | 2018-08-06 | [5 empty] | Y |  |  |  |  | Neither
130265 | 18/SC/0155 | 236211 | The EMPA-KIDNEY Study | No |  | 88 |  |  | 2018-04-20 | 2018-06-07 | 2018-04-26 | 2018-07-04 | 2018-09-03 | 2018-09-03 |  |  |  | Y | [6 empty] | Sponsor
130266 | 17/EM/0406 | 235483 | PRTX-100 in ITP (PRTX-100-202) | No |  |  |  |  | 2018-06-05 | 2018-06-07 | 2018-01-15 | [5 empty] | Y | [7 empty] | Sponsor
130267 | 17/LO/1596 | 228894 | REACH Pregnancy Circles Trial ; Version 1.0 | No |  |  |  |  | 2018-06-01 | 2018-06-08 | 2018-05-30 | [6 empty] | Y | [6 empty] | Sponsor
130268 | 18/NE/0214 | 245998 | MN39158 - A Long Term Extension Study in Multiple Sclerosis | Yes | 2018-11-14 | 84 | 65 | 149 | 2018-04-18 | 2018-06-18 | 2018-07-11 | 2018-07-19 | 2018-09-10 | 2018-09-10 | [5 empty] | Y |  |  |  |  | Neither
130269 | 17/EE/0422 | 230642 | M16-098 | Yes | 2018-04-09 | 24 | 45 | 69 | 2017-10-11 | 2018-01-30 | 2018-01-29 | 2018-02-16 | 2018-02-23 | 2018-03-06 | [10 empty] | Please Select...
130270 | 17/EE/0437 | 233853 | AQUILA (54767414SMM3001) | Yes | 2018-05-10 | 14 | 56 | 70 | 2017-10-27 | 2018-03-01 | 2018-01-10 | 2018-02-05 | 2018-03-15 | 2018-04-03 | [10 empty] | Please Select...
130271 | 17/SC/0652 | 235511 | SHP647 long term extension for moderate to severe Ulcerative Colitis | No |  | 135 |  |  | 2018-01-10 | 2018-03-20 | 2018-03-06 | 2018-07-17 | 2018-08-02 | 2018-08-06 | [5 empty] | Y |  |  |  |  | Neither
130272 | 18/EM/0086 | 236856 | A study of Mavenclad? in participants with multiple sclerosis | No |  | 111 |  |  | 2018-05-18 | 2018-05-23 | 2018-05-22 | 2018-08-28 | 2018-09-11 | 2018-09-12 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
130273 | 18/LO/0448 | 241283 | CALDOSE - 1 | Yes | 2018-12-17 | 86 | 94 | 180 | 2018-06-20 | 2018-06-20 | 2018-05-03 | 2018-06-26 | 2018-09-14 | 2018-10-22 |  |  |  | Y |  | Y |  |  |  |  | Both
130274 | 17/LO/2043 | 236939 | Development Of a haemophiLia physiotherapy intervention - Version 1 | Yes | 2018-09-20 | 68 | 23 | 91 | 2018-06-21 | 2018-06-21 | 2018-05-25 | 2018-08-24 | 2018-08-28 | 2018-08-29 | [7 empty] | Y |  |  | Both
130275 | 17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | Yes | 2018-07-16 | 17 | 5 | 22 | 2017-03-17 | 2018-06-24 | 2017-05-26 | 2018-07-11 | 2018-07-11 | 2018-07-11 | [10 empty] | Please Select...
130276 | 18/NE/0102 | 240702 | CA40192:Etrolizumab in patients with moderate to severe UC or CD | No |  | 8 |  |  | 2018-03-19 | 2018-07-04 | 2018-05-15 | 2018-07-05 | 2018-07-12 | 2018-07-12 | [5 empty] | Y |  |  |  |  | Neither
130277 | 17/NE/0113 | 210677 | The PIONEER Study | No |  | 4 |  |  | 2018-03-26 | 2018-09-17 | 2017-05-24 | 2018-09-11 | 2018-09-21 | 2018-09-28 | [5 empty] | Y |  |  |  |  | Neither
130278 | 17/NE/0082 | 217397 | Phase 3 study with subjects with Moderately to Severely Active RA with IR or Intolerance to bDMARDs | No |  | 53 |  |  | 2018-06-22 | 2018-07-09 | 2017-06-02 | 2018-08-23 | 2018-08-31 | 2018-09-04 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
130279 | 16/EE/0324 | 203951 | Prophylatic and Pre-emptive DLI for myeloid malignancies (PRO-DLI) | No |  | 113 |  |  | 2018-04-01 | 2018-07-12 | 2016-09-08 | 2018-10-17 | 2018-11-02 | 2018-11-14 | [7 empty] | Y | Y |  | Both
130280 | 18/NW/0037 | 234353 | REDUCE-RISKinCD-PIBD -TRIAL | Yes | 2018-11-27 | 114 | 20 | 134 | 2018-07-16 | 2018-07-16 | 2018-07-12 | 2018-10-29 | 2018-11-07 | 2018-11-07 | [7 empty] | Y |  |  | NHS Provider
130281 | 17/LO/1629 | 228288 | Phase 1b study in patients with advanced or solid tumours | Yes | 2018-09-05 | 23 | 27 | 50 | 2017-10-19 | 2018-07-17 | 2017-11-06 | 2018-06-27 | 2018-08-09 | 2018-08-28 | [10 empty] | Please Select...
130282 | 18/LO/0378 | 234232 | PIONEER III | Yes | 2018-09-07 | 36 | 16 | 52 | 2018-04-23 | 2018-07-17 | 2018-06-22 | 2018-08-16 | 2018-08-22 | 2018-08-28 | [10 empty] | Please Select...
130283 | 18/YH/0069 | 242258 | GLOW study | Yes | 2018-09-05 | 35 | 14 | 49 | 2018-02-06 | 2018-07-18 | 2018-06-04 | 2018-08-15 | 2018-08-22 | 2018-09-03 | [10 empty] | Please Select...
130284 | 18/SC/0037 | 234222 | GO39942 / RO5541007 in lymphoma | No |  | 27 |  |  | 2018-02-27 | 2018-07-18 | 2018-04-16 | 2018-08-06 | 2018-08-14 | 2018-10-24 | [7 empty] | Y |  |  | NHS Provider
130285 | 18/LO/0397 | 237296 | MORPHEUS-TNBC | Yes | 2018-08-14 | 21 | 4 | 25 | 2018-03-15 | 2018-07-20 | 2018-06-08 | 2018-08-06 | 2018-08-10 | 2018-08-10 | [10 empty] | Please Select...
130286 | 17/NE/0311 | 229481 | GO39733 | Yes | 2018-09-12 | 25 | 19 | 44 | 2017-09-08 | 2018-07-30 | 2017-11-22 | 2018-08-06 | 2018-08-24 | 2018-09-04 | [10 empty] | Please Select...
130287 | 17/LO/0980 | 219505 | HALT - Stereotactic Body Radiotherapy for the treatment of OPD | No |  | 76 |  |  | 2018-02-23 | 2018-08-10 | 2017-07-10 | 2018-10-16 | 2018-10-25 | 2018-10-29 | [5 empty] | Y |  |  |  | Y | Neither
130288 | 18/YH/0133 | 239570 | GO40241 - Phase III - Neoadjuvant Atezolizumab + Chemotherapy in NSCLC | No |  | 112 |  |  | 2018-04-11 | 2018-08-10 | 2018-05-17 | 2018-11-07 | 2018-11-30 | [11 empty] | Please Select...
130289 | 18/WA/0104 | 236930 | P3100:pevonedistat+azacitidine for HR MDS/CMML/low blast AML treatment | No |  | 64 |  |  | 2018-03-02 | 2018-08-14 | 2018-04-29 | 2018-10-08 | 2018-10-17 | 2018-11-06 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
130290 | 18/SW/0038 | 235662 | The LoDED Trial | Yes | 2018-10-11 | 49 | 7 | 56 | 2018-08-13 | 2018-08-16 | 2018-04-26 | 2018-10-02 | 2018-10-04 | 2018-10-08 | [10 empty] | Please Select...
130291 | 18/LO/0555 | 237992 | PROTECTOR | Yes | 2018-11-01 | 61 | 15 | 76 | 2018-08-17 | 2018-08-17 | 2018-04-19 | 2018-10-17 | 2018-10-17 | 2018-11-01 | [10 empty] | Please Select...
130292 | 18/LO/1398 | 247563 | Diabetic Gastroparesis Study with Randomized-withdrawal Period | No |  |  |  |  | 2018-08-22 | 2018-08-22 | 2018-11-06 | [13 empty] | Please Select...
130293 | 18/NE/0142 | 242919 | The REVERSE study | Yes | 2018-11-05 | 45 | 18 | 63 | 2018-07-13 | 2018-09-03 | 2018-07-13 | 2018-10-05 | 2018-10-18 | 2018-10-10 | [10 empty] | Please Select...
130294 | 16/YH/0157 | 204585 | PLATO?-?PersonaLising?Anal?cancer?radioTherapy?dOse | No |  | 22 |  |  | 2017-05-17 | 2018-09-04 | 2016-07-20 | 2018-09-21 | 2018-09-26 | 2018-09-28 | [5 empty] | Y |  |  |  |  | NHS Provider
130295 | 18/LO/1542 | 247189 | Phase 2 study to test the efficacy & safety of KPL 301 in GCA | No |  |  |  |  | 2018-07-24 | 2018-09-04 | 2018-12-06 | [13 empty] | Please Select...
130296 | 18/SW/0135 | 232687 | TULIP: Surgical vs non-surgical treatment of LC1 pelvic injuries | Yes | 2018-12-24 | 90 | 20 | 110 | 2018-07-27 | 2018-09-05 | 2018-07-04 | 2018-11-16 | 2018-12-04 | 2018-12-04 | [5 empty] | Y |  |  |  |  | Neither
132931 | 13/LO/1837 | 102551 | Radiocyst 01 | No |  | 34 |  |  | 2017-12-18 | 2018-03-16 | 2016-07-06 | 2018-04-10 | 2018-04-19 | 2018-03-16 | [5 empty] | Y |  |  | Y |  | Neither
132932 | 17/EE/0361 | 231209 | SPIRIT | No |  | 87 |  |  | 2018-03-20 | 2018-03-20 | 2017-10-31 | 2018-05-03 | 2018-06-15 |  |  |  | Y | [7 empty] | Sponsor
132933 | 17/SC/0394 | 229032 | A Phase 2 Dose-Finding Study of Pacritinib in Myelofibrosis Patients | Yes | 2018-11-23 | 91 | 53 | 144 | 2018-05-30 | 2018-07-02 | 2017-10-23 | 2018-08-09 | 2018-10-01 | 2018-10-30 |  |  |  |  | Y | [5 empty] | NHS Provider
132934 | 17/LO/0038 | 182633 | UK P3BEP Trial | Yes | 2018-11-15 | 14 | 42 | 56 | 2017-05-22 | 2018-09-20 | 2017-04-06 | 2018-06-02 | 2018-10-04 | 2018-10-15 | [10 empty] | Please Select...
132935 | 18/SC/0342 | 247085 | Phase III Trial of AMT-061 in adults with haemophilia B | No |  | 23 |  |  | 2018-06-11 | 2018-09-12 | 2018-09-06 | 2018-09-26 | 2018-10-05 | 2018-11-22 | [5 empty] | Y |  |  |  |  | Sponsor
132936 | 16/LO/1099 | 181655 | TIGER: A RANDOMIZED PHASE III TRIAL COMPARING CONVENTIONAL-DOSE CHEMOTHERAPY | Yes | 2018-11-15 | 26 | 37 | 63 | 2017-10-03 | 2018-09-13 | 2016-11-01 | 2018-10-02 | 2018-10-09 | 2018-11-06 | [10 empty] | Please Select...
132937 | 16/EE/0315 | 197289 | Metformin SGA study version 1.2 | No |  | 193 |  |  | 2018-03-20 | 2018-04-12 | 2016-11-21 | 2018-09-05 | 2018-10-22 | 2018-10-22 |  |  |  | Y | [6 empty] | Sponsor
132938 | 18/NI/0060 | 242168 | Lenabasum in Cystic Fibrosis | No |  | 2 |  |  | 2018-07-16 | 2018-10-23 | 2018-06-29 | 2018-10-04 | 2018-10-25 | 2018-12-03 | [5 empty] | Y |  |  |  |  | Neither
132939 | 18/EM/0193 | 243749 | 021FSG16010 - DUPLEX, Patients with FSGS | No |  | 35 |  |  | 2018-08-14 | 2018-09-24 | 2018-09-18 | 2018-10-24 | 2018-10-29 | 2018-11-20 | [5 empty] | Y |  |  |  |  | Neither
132940 | 18/EM/0148 | 236593 | Durvalumab + BCG in NMIBC | No |  | 29 |  |  | 2018-05-24 | 2018-10-02 | 2018-07-16 | 2018-10-24 | 2018-10-31 | 2018-11-08 | [5 empty] | Y |  |  |  |  | Neither
132941 | 18/LO/1120 | 246006 | Enfortumab Vedotin vs. chemotherapy in advanced or metatstatic urothel | Yes | 2018-11-08 | 23 | 7 | 30 | 2018-06-06 | 2018-10-09 | 2018-09-18 | 2018-10-24 | 2018-11-01 | 2018-11-07 | [10 empty] | Please Select...
132942 | 17/NW/0698 | 233163 | IMMU-132 in Breast Cancer | Yes | 2018-11-26 | 35 | 20 | 55 | 2018-05-23 | 2018-10-02 | 2018-05-02 | 2018-11-01 | 2018-11-06 | 2018-11-19 | [10 empty] | Please Select...
132943 | 18/LO/1583 | 239032 | BYPASS-CTCA | Yes | 2018-11-15 | 11 | 9 | 20 | 2018-10-26 | 2018-10-26 | 2018-10-19 | 2018-11-05 | 2018-11-06 | 2018-11-14 | [10 empty] | Please Select...
132944 | 18/LO/0864 | 245423 | Safety & efficacy of Venetoclax + Fulvestrant in ER+ MBC patients | Yes | 2018-11-23 | 38 | 14 | 52 | 2018-03-28 | 2018-10-02 | 2018-07-12 | 2018-11-01 | 2018-11-09 | 2018-11-22 | [10 empty] | Please Select...
132945 | 18/EM/0112 | 236871 | ALL-RIC | No |  | 21 |  |  | 2018-04-23 | 2018-10-19 | 2018-06-12 | 2018-10-26 | 2018-11-09 | 2018-11-23 | [5 empty] | Y |  |  |  |  | Neither
132946 | 18/ES/0102 | 236940 | Bio-T-App | Yes | 2018-12-11 | 7 | 27 | 34 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-14 | 2018-11-14 | 2018-12-17 | [10 empty] | Please Select...
132947 | 18/SC/0502 | 246134 | ACI-24-1801 | No |  | 43 |  |  | 2018-10-05 | 2018-10-10 | 2018-10-15 | 2018-11-19 | 2018-11-22 | [6 empty] | Y |  |  |  |  | Neither
132948 | 18/LO/1276 | 233887 | PINBALL | No |  | 57 |  |  | 2018-07-16 | 2018-10-02 | 2018-10-02 | 2018-11-28 | 2018-11-28 | 2018-11-29 | [5 empty] | Y |  |  |  |  | Neither
132949 | 18/NE/0078 | 235552 | SETS aHUS: Stopping Eculizumab Treatment Safely in aHUS | No |  | 54 |  |  | 2018-08-03 | 2018-10-05 | 2018-04-13 | 2018-10-22 | 2018-11-28 | 2018-11-28 | [5 empty] | Y |  |  |  |  | Neither
132950 | 18/EM/0113 | 236887 | MOR106-CL-201_Phase II_Atopic Dermatitis_IV MOR106 | No |  | 28 |  |  | 2018-04-30 | 2018-11-02 | 2018-05-09 | 2018-11-07 | 2018-11-30 | [6 empty] | Y |  |  |  |  | Neither
132951 | 18/LO/0500 | 230104 | MORPHEUS - GASTRIC CANCER | No |  |  |  |  | 2018-03-15 | 2018-03-15 | 2018-07-17 | [5 empty] | Y | [7 empty] | Sponsor
132952 | 17/NW/0678 | 233267 | INS1007-201 - The Willow Study | No |  |  |  |  | 2018-02-23 | 2018-06-13 | 2018-07-26 | [5 empty] | Y | [7 empty] | Sponsor
132953 | 18/LO/1111 | 248674 | SOAR | No |  |  |  |  | 2018-06-15 | 2018-06-15 | [6 empty] | Y | [7 empty] | Sponsor
132954 | 18/EE/0136 | 243704 | Efficacy and Safety of Bimekizumab in Chronic Plaque Psoriasis | No |  |  |  |  | 2018-03-27 | 2018-07-16 | [6 empty] | Y | [7 empty] | Sponsor
132955 | 18/LO/0722 | 238635 | A Phase 3 study of Ozanimod as induction therapy for Crohn?s Disease | No |  |  |  |  | 2018-05-01 | 2018-08-16 | 2018-07-30 | [6 empty] | Y | [6 empty] | Sponsor
132956 | 18/LO/0996 | 244434 | LV Only MPP with SyncAV | No |  | 87 |  |  | 2018-09-14 | 2018-09-17 | 2018-09-04 |  | 2018-12-13 | 2018-12-19 |  |  |  | Y | [6 empty] | Both
132957 | 18/LO/1038 | 228625 | Remote monitoring & gaming technology for children with CF | Yes | 2019-01-03 | 81 | 24 | 105 | 2018-08-03 | 2018-09-20 | 2018-08-23 | 2018-12-10 | 2018-12-10 | 2018-12-10 |  |  |  |  | Y | [5 empty] | NHS Provider
132958 | 18/LO/2062 | 237959 | Administering Cryoprecipitate in Obstetric Bleeding at an Earlier Time | No |  |  |  |  | 2018-09-21 | 2018-09-21 |  |  |  |  | Y | [9 empty] | Neither
132959 | 18/NE/0139 | 240364 | TAK954-2002 | No |  |  |  |  | 2018-05-14 | 2018-09-26 | 2018-06-12 | [5 empty] | Y | [7 empty] | Sponsor
132960 | 18/LO/1172 | 245733 | Phase 2 Study Comparing CB839 & Cabo vs. Placebo & Cabo in Adv RCC | No |  | 71 |  |  | 2018-08-17 | 2018-10-02 | 2018-08-10 | 2018-12-04 | 2018-12-12 | 2019-01-04 |  |  |  |  | Y |  |  | Y |  |  | Both
132961 | 17/WS/0187 | 220456 | RESHAPE-HF2 | No |  |  |  |  | 2018-01-05 | 2018-10-17 | 2018-03-20 | [6 empty] | Y |  |  |  | Y |  |  | Sponsor
132962 | 18/LO/1791 | 246700 | Study of effectiveness and safety of a treatment for children with RSV | No |  |  |  |  | 2018-10-05 | 2018-12-06 | 2018-12-05 | [13 empty] | Please Select...
132963 | 18/LO/0995 | 244737 | Lenvatinib plus Pembrolizumab to Treat Advanced Endometrial Cancer | No |  | 55 |  |  | 2017-12-14 | 2018-10-27 | 2018-09-20 | 2018-12-13 | 2018-12-21 | 2019-01-04 | [10 empty] | Please Select...
132964 | 18/SC/0243 | 240684 | ORION-4 | No |  |  |  |  | 2018-05-23 | 2018-11-02 | 2018-10-01 | [13 empty] | Please Select...
132965 | 18/SC/0614 | 251365 | PTG-300 in NTD and TD ?-Thalassaemia patients with Chronic Anaemia | No |  |  |  |  | 2018-09-26 | 2018-11-06 | [14 empty] | Please Select...
132966 | 18/LO/1805 | 246414 | JAVELIN BRCA/ATM | No |  |  |  |  | 2018-08-08 | 2018-11-07 | [14 empty] | Please Select...
132967 | 17/LO/0568 | 215024 | Motivating Structured walking Activity in Intermittent Claudication (MOSAIC) | No |  |  |  |  | 2018-08-28 | 2018-11-09 | 2017-04-27 | [13 empty] | Please Select...
132968 | 17/NI/0096 | 225743 | HOPE-1 | No |  |  |  |  | 2018-10-25 | 2018-11-09 | 2017-07-14 | [13 empty] | Please Select...
132969 | 18/LO/1922 | 251251 | Study to Evaluate the Effect of GBT440 in Pediatrics with Sickle Cell | No |  |  |  |  | 2018-08-14 | 2018-11-13 | [14 empty] | Please Select...
132970 | 18/LO/1492 | 248861 | PRAETORIAN-DFT | No |  |  |  |  | 2018-11-12 | 2018-11-14 | 2018-11-12 | [13 empty] | Please Select...
132971 | 18/WA/0161 | 238902 | WISARD: DTG+RPV FDC in patients with HIV-1 and the K103N mutation | No |  |  |  |  | 2018-11-15 | 2018-11-15 | 2018-10-04 | [13 empty] | Please Select...
132972 | 18/EM/0307 | 241127 | PROMOTE food in inflammatory bowel disease | No |  |  |  |  | 2018-10-18 | 2018-11-15 | 2018-11-09 | [13 empty] | Please Select...
132973 | 18/SC/0242 | 238151 | BLING III study | No |  |  |  |  | 2018-11-14 | 2018-11-19 | 2018-08-24 | [13 empty] | Please Select...
132974 | 18/SC/0428 | 239952 | GO39932 | No |  |  |  |  | 2018-09-28 | 2018-11-21 | 2018-11-16 | [13 empty] | Please Select...
132975 | 18/SW/0047 | 232201 | DIPLOMA trial version 1.0 | No |  |  |  |  | 2018-11-23 | 2018-11-23 | 2018-03-15 | [13 empty] | Please Select...
132976 | 18/LO/0071 | 229507 | A-BRAVE Trial | No |  | 8 |  |  | 2017-10-10 | 2018-11-26 | 2018-04-03 | 2018-11-27 | 2018-12-04 | 2018-12-07 | [10 empty] | Please Select...
132977 | 18/WA/0092 | 230113 | Ustekinumab in adolescents with recent-onset type 1 diabetes (USTEKID) | No |  |  |  |  | 2018-11-26 | 2018-11-26 | 2018-09-21 | [13 empty] | Please Select...
132978 | 18/LO/1453 | 246119 | BARBICAN | No |  | 22 |  |  | 2018-08-13 | 2018-11-27 | 2018-11-15 | 2018-12-14 | 2018-12-19 | 2018-12-21 | [10 empty] | Please Select...
Note on A1: System generated field
Note on G1: System generated field. Please check your dates if value is negative.
Note on J1: Format dd/mm/yyyy.
Note on K1: Format dd/mm/yyyy.
Note on L1: Format dd/mm/yyyy.
Note on M1: Format dd/mm/yyyy.
Note on N1: Format dd/mm/yyyy.
Note on O1: Format dd/mm/yyyy.